## Web
Puffy Paws 23 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 24 | 3 | BA | 1 | 3 | 3
Project Management | 94.25 | 11.7812 | Tech Writer | 1 | 3 | 3
SRS,FS,User Manual | 24 | 3 | PM | 1 | 11.7812 | 11.7812
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 1 | 59 | 59 | 118 | 117.8125
Development |  |  | Sr Developer | 1 | 59 | 59
Application Basic setup | 0 | 0 | Mobile API | 1 | 23.5625 | 23.5625
User Registration |  |  | QA | 2 | 23.6172 | 47.2344
Home page | 8 | 1 | Total |  |  | 216.5781
Forgot password with OTP | 4 | 0.5
Remember password | 4 | 0.5 |  | Days | Months
Registration | 6 | 0.75 | Total Effort | 216.5781 | 10.8289
OTP verification | 6 | 0.75 | Delivery Timeline | 95.6172 | 4.7809
Login | 6 | 0.75
Choose emirate | 4 | 0.5
Choose pet type | 4 | 0.5
Services & Products
Services listing | 8 | 1
Product listing | 8 | 1
Services in locality (search) | 8 | 1
Services in facility (Search) | 4 | 0.5
Service details for an instance (Service offerings + Prices + Description + Profile + pictures) | 8 | 1
Services offered by pet | 4 | 0.5
Book service ( Pick time & date based on existing schedule) : slots | 8 | 1
Checkout (edit cart – add , delete) | 8 | 1
Bill summary (Bill details + taxes + total amount + delivery charges) | 6 | 0.75
Apply discount vouchers | 4 | 0.5
Make payment (billing address, delivery address, credit card details) | 8 | 1
Search products by locality or category + other criteria | 6 | 0.75
List shops | 6 | 0.75
Shop page ( List products, prices & description + pictures-thumbnails) | 6 | 0.75
Product details (images + description + prices ) | 6 | 0.75
Checkout (edit cart -add, delete) | 6 | 0.75
Bill summary (Bill details + taxes + total amount + delivery charges) | 4 | 0.5
Cash on delivery option | 4 | 0.5
Apply discount vouchers | 4 | 0.5
Make payment (billing address, delivery address, credit card details) | 8 | 1
Order Confirmation (for both products & services) | 6 | 0.75
Push notifications -> Receive SMS + email notifications of order details (Services + products) | 16 | 2
Integrations
Strype payment gateway | 16 | 2
email | 6 | 0.75
SMS | 8 | 1
OTP generation | 4 | 0.5
My Account (customer)
View Profile | 6 | 0.75
Edit profile | 6 | 0.75
Add / Edit addresses (multiple) | 4 | 0.5
Select language | 40 | 5 | Multilingiual considered only for Arabic & English
Manage payment card details | 6 | 0.75
Change password with OTP | 6 | 0.75
About Us | 4 | 0.5
FAQ | 4 | 0.5
Privacy policy | 4 | 0.5
T & C | 4 | 0.5
Contact Us with a simple form | 4 | 0.5
Orders Placed | 6 | 0.75
Orders completed | 4 | 0.5
Orders Cancelled | 4 | 0.5
Providers (available to logged in users)
provider Registration (on main site menu) | 6 | 0.75
Provider dashboard (incoming orders + Bookings + Completed Transations) | 16 | 2
Realtime notifications with alerts | 12 | 1.5
Order details + customer details /w delivery address | 6 | 0.75
Transaction details | 4 | 0.5
Reports on best selling products & services, total order by day/week/month, Total amount received by day/week/month | 16 | 2
Add / manage products (name, description, images, prices, discounts) | 16 | 2
Add / manage services (name , description, images, prices, discounts) | 16 | 2
manage service schedules | 10 | 1.25
Manage vouchers for services & products (date range, discount, shop, product, service) | 16 | 2
Communication dashboard to send / receive notification to customers / providers / admins | 24 | 3
Update profile | 4 | 0.5
Customer care Agent
Customer care dashboard (Orders received, Orders completed) | 16 | 2
Order cancellations | 6 | 0.75
Manage disputes | 6 | 0.75
Replace orders | 12 | 1.5
refill orders | 6 | 0.75
Track orders | 6 | 0.75
Cancel and book service slots | 8 | 1
reschedule service slots | 6 | 0.75
Update order status | 4 | 0.5
Communication dashboard to send / receive notification to customers / providers / admins | 4 | 0.5
Admin
Create provider accounts | 4 | 0.5
Create customer care agents | 4 | 0.5
Update customer info | 4 | 0.5
Hold & Activate provider activities | 8 | 1
Access audit trail of activities conducted by Customer care Agent | 12 | 1.5
View audit trail of providers | 12 | 1.5
Dashboard for analytics related to the performance of the platform | 24 | 3
Add advertisements / display advertisements on site | 16 | 2
Rank provider priority in search listings | 12 | 1.5
Manage products / prices | 6 | 0.75
Manage vouchers for services & products (date range, discount, shop, product, service) | 16 | 2
Communication dashboard to send / receive notification to customers / providers / admins | 4 | 0.5
System
Auditing & logging (CCA + Providers + customers) | 12 | 1.5
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
Authentication, Authorization, Roles | 6 | 0.75
Exception Handling and Error logging | 6 | 0.75
Notification management | 6 | 0.75
Reporting Engine | 6 | 0.75
Workflow management | 16 | 2
Search Engine | 6 | 0.75
Mobile API
Mobile api | 188.5 | 23.5625
SQA
QA & Bug fixing | 329.875 | 41.2344
UAT | 40 | 5
Deployment | 8 | 1
Total | 1542.625 | 192.8281
vvvcnmnmvbn

## Mobile
PuffyPaws 23 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1 |  | 0
User Registration |  |  |  |  | iOS Developer | 1 |  | 0
Splash Screen |  |  |  |  | QA | 1 | 0 | 0
Forgot password with OTP |  |  |  |  | Total |  |  | 0
Remember password
Registration
OTP verification
Login
Choose emirate
Choose pet type
Services & Products
Services listing
Product listing
Services in locality (search)
Services in facility (Search)
Service details for an instance (Service offerings + Prices + Description + Profile + pictures)
Services offered by pet
Service description page
Book service ( Pick time & date based on existing schedule) : Slots
Checkout (edit cart – add , delete)
Bill summary (Bill details + taxes + total amount + delivery charges)
Apply discount vouchers
Make payment (billing address, delivery address, credit card details)
Search products by locality or category + other criteria
List shops
Shop page ( List products, prices & description + pictures-thumbnails)
Product details (images + description + prices )
Chaeckout (edit cart -add, delete)
Bill summary (Bill details + taxes + total amount + delivery charges)
Cash on delivery option
Apply discount vouchers
Make payment (billing address, delivery address, credit card details)
Order Confirmation (for both products & services)
Push notifications -> Receive SMS + email notifications of order details (Services + products)
Integrations
Strype payment gateway
email
SMS
OTP generation
My Account
View Profile
Edit profile
Add / Edit addresses (multiple)
Select language
Manage payment card details
Change password
About Us
FAQ
Privacy policy
T & C
Contact Us with a simple form
Orders Placed
Orders completed
Orders Cancelled
SQA
QA & Bug fixing
UAT
Deployment
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.