## MOHRE
| RRC Tender Management |  | 13/7/2020
Monday
| Module | Hours | Man Days | Resource | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 17 | 17 | 34.5 | 38.45 | 34.5 | 35
2 | Project Management | 27.6 | 3.45 | Jr Developer | 1 | 18 | 18
3 | SRS,FS,User Manual | 24 | 3 | PM | 1 | 3.45 | 3.45
4 | Design and Prototype | 32 | 4 | BA | 1 | 4 | 4
| Development |  |  | Tech writer | 1 | 3 | 3
5 | Application basic setup | 8 | 1 | QA | 1.5 | 10.55 | 15.825
| New Development |  |  | Total |  | 60 | 65.275
| Tender Management |  |  | - | - | - | -
| User Entitlements (Creater, Admin, Comm Members, HOC) | 12 | 1.5 | Effort | 65.275 |  |  |  |  | 8.1594
| manage Committee members | 8 | 1 | Delivery Time | 32.55 |  |  |  |  | 1.6275
| Manage Supplier List | 6 | 0.75
| Receive Tender request | 6 | 0.75
| Create Tender (requesters, Suppliers, Start & close time etc) | 12 | 1.5
| Distribute tenders | 12 | 1.5
| Send reminder emails | 6 | 0.75
| Tender Submission page with attachments for suppliers | 8 | 1
| Automated Tender review request emails to comm. Members | 6 | 0.75
| Tender Management Dashboard (List tenders, Tender review counts, Open tenders, closed tenders etc) | 16 | 2
| Tender details page (read only) | 8 | 1
| Tender review page (Comments, votes, Fiscal & Technical evaluation scores etc) | 12 | 1.5
| Send tender clarifications to supplier, receive & log supplier updates | 8 | 1
| HOC review based on consolidated view of all attachments and comments from comm members | 16 | 2
| HOC nominatiions for primary and standby suppliers | 6 | 0.75
| Change Tender status to awarded | 4 | 0.5
Committee Management
| Create new project (Requester, subject, details, attachments, deadlines etc) | 12 | 1.5
| Distribute project details to Comm. Members via automated email | 8 | 1
| View project details | 12 | 1.5
| Committee members review project. Add attachments and comments | 12 | 1.5
| Send reminder emails to committee members when project deadline approaches | 6 | 0.75
| HOC has consolidated view of all comments and attachements from members | 16 | 2
| HOC nominates project with reccomendations | 6 | 0.75
System Features
| User management | 6 | 0.75
| Authentication, Authorization, Entitlements | 4 | 0.5
| Auditing and Logging | 4 | 0.5
| Managing Exceptions and Errors | 4 | 0.5
| Communication Management | 4 | 0.5
Security Features
| Protection against injection (SQL, CRLF, LDAP) | 4 | 0.5
| URL encoding, Input validation | 4 | 0.5
| Cookie Encryption, Cookie replay attacks | 4 | 0.5
| Session hijacking prevention | 4 | 0.5
| Cross site scripting and session management | 4 | 0.5
| Auditing and logging | 4 | 0.5
| Exceptions and error handling | 4 | 0.5
Quality Assurance
| QA & Bug Fixing | 96.6 | 12.075
| UAT | 24 | 3
| Deployment per instance | 6 | 0.75
| Total Effort |  | 64.775
Assumptions
Maintenance shall be on Time and Material