## MOJ
| Maintenance electronic link interface s/m with text messages |  | 2020-08-04
Wednesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 0 | 0 | 26.5 | 29.9425 | 26.5 | 26
2 | Project Management | 31.54 | 3.9425 | Jr Developer | 1 | 26 | 26
3 | SRS,FS,User Manual | 32 | 4 | PM | 1 | 3.9425 | 3.9425
4 | Design and Prototype | 32 | 4 | BA | 1 | 4 | 4
| Development |  |  | Tech writer | 1 | 4 | 4
5 | Application basic setup | 8 | 1 | QA | 1.5 | 7.95 | 11.925
| Functional Requirements |  |  | Total | 7.5 | 49.8925 | 53.8675
| SMS in Arabic & English | 12 | 1.5
| Message scheduling for sending it in future date | 20 | 2.5 | Effort | 53.8675 | + 1 Day (Deployment)
| Get message status | 8 | 1 | Delivery Time | 41.95 | + 1 Day (Deployment)
| SMS to single mobile number | 4 | 0.5
| SMS to group or list of mobile numbers | 12 | 1.5
| Maximum characters in English 1000(single message) | 4 | 0.5
| Maximum characters in Arabic 340(single message) | 4 | 0.5
| A module to integrate the web service with any current or new systems to send SMS | 20 | 2.5
| API for third party to integrate to the system with clear documentation | 32 | 4
| PUSH/PULL | 8 | 1
| Validation for web services | 8 | 1
| Handling of error and delivery reports (1 tabular report) | 8 | 1
| Add Reports |  | 0
| Summary & detailed reports (3 tabular reports) | 24 | 3
0
Integration Requirements
| Netpiper sms | 8 | 1
| smsSlobal | 16 | 2
| SmartCall | 16 | 2
Quality Assurance
| QA & Bug Fixing | 71.4 | 8.925
| UAT | 24 | 3
| Deployment per instance | 8 | 1
| Total Effort | 442.94 | 55.3675
Assumptions
SMS provider would support both arabic & englisgh
PUSH/PULL need clarification
Message status can be queried from the SMS provider