## Static Preference
e-Dirham Integration Project | July 21 2017 | July 21 2017
| Wednesday | Wednesday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 16 | 2 | 2
Functional Specification | 0 | 0 | Sr.Developer | 1 | 96 | 12 | 12 | 24 | 24
Project Management | 19.2 | 2.4 | Jr Developer | 1 | 96 | 12 | 12
Graphic Design | 8 | 1 | PM | 1 | 27.2 | 3.4 | 3.4
Working Prototype | 8 | 1 | QA | 2 | 30.8 | 3.85 | 7.7
Development |  |  | Total |  | 266 |  | 37.1 | 296.8
Step 1 |  | 0
Create data file from step 1 from HHI data | 4 | 0.5 | Total Delivery days | 17.85
Step 2 |  | 0 | Total Man day Effort | 37.1 | 27.825
Create new calculated attributes from HHI | 4 | 0.5
selection criteria for most relevant person for SP(Static Preference) | 8 | 1
Identify the most preferable SP for the selected person | 8 | 1
Step 3 |  | 0
Attitude ranking Questions | 12 | 1.5
Step 4 |  | 0
Description and rules for the Static Pereference ranking game | 8 | 1
Step 5 |  | 0
Conduct the Static Preference game using predefined rules and algorithm | 22 | 2.75
Step 6 |  | 0
Questions on the SP games being conducted | 14 | 1.75
Step 7 |  | 0
Calculate the output of the survey and convert it to data file (Visual interface results) | 16 | 2
System functions |  | 0
Calculate trip time, fare cost, interchange time etc | 8 | 1
Admin |  | 0
Create Users, roles, user Login, authentication etc | 16 | 2
Logging, auditing etc | 8 | 1
Create introductory statement | 8 | 1
Create attitudinal ranking questions | 16 | 2
Create game descriptions | 8 | 1
Manage lookup tables | 8 | 1
Create games, Blocks and Modes | 16 | 2
Step 7 calculations | 8 | 1
Testing & Deployment
Testing | 57.6 | 7.2
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 300.8 | 37.6
Assumptions
Device/s and required SDK and Test cards will be provided by the client
Merchant ID and other required payment gateway details will be provided by the client
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions