## EMIS
Educational Management Information System |  | Nov 16 2017
| Somalialand | Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 32 | 4 | 4
Functional Specification | 8 | 1 | Web Developer | 1 | 0 | 0 | 0 | 0 | 0
Project Management | 0 | 0 | Mobile developer | 1 | 0 | 0 | 0
Graphic Design | 16 | 2 | PM | 1 | 16 | 2 | 2
Working Prototype | 16 | 2 | QA | 2 | 2 | 0.25 | 0.5
Development |  |  | Total |  | 50 |  | 6.5 | 52
Admin Module
User Management |  |  | Total Delivery days | 4.25
Manage projets |  | 0 | Total Man day Effort | 6.5
Manage Servcices |  | 0
Manage Companies |  | 0
0
0
0
0
0
0
Human Resources Module
0
Testing & Deployment
Testing | 0 | 0
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 60 | 7.5
Assumptions
The application will be a responsive web application
Survey Template | Design | Development