## SobhaGroup
| SobhaGroup | 2018-05-03
Wednesday
Sl. No. | Module | Man Hours
1 | Analysis and Planning
2 | UI/UX | 20 | Resource | No | Hrs | ManDays
3 | Documentation | 8 | UI/UX | 1 | 20 | 2.5
4 | Project Management | 26.4 | BA | 1 | 8 | 1
5 | Development and Production |  | PM | 1 | 26.4 | 3.3
6 | Set up development environment and server - PHP | 0 | Developer | 1.5 | 176 | 33
7 | Admin - |  | QA | 2 | 46.2 | 11.55
8 | Dashboard | 8 | Total |  | 276.6 | 51.35
7 | Manage Users | 5
8 | Manage Project Type | 5 | Delivery Days | 30.275
11 | Manage Service Type | 5 | Total Effort | 51.35
12 | Manage Companies | 5
13 | Manage Project
14 | Project info | 8
15 | Create 2D elevation Drawing | 32
17 | Design Department | 80
18 | Enter Building Data
19 | Add Windows
Dynamic Screen designs and updates
| Production Department | 80
Update Work Progress
System Alerts
Production department workflow
Screen Updates
| Application workflow | 24
| Management Reports Dashboard | 12
Testing and training
| Test for full functionality on all major and active browsers | 92.4
| Total | 410.8
Assumptions