## Web
SPORTLR 24 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 56 | 7 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 7 | 7
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 1 | 0 | 0 | 0 | 0
Development |  |  | Sr Developer | 1 | 0 | 0
|  |  | Mobile API | 1 | 22.7 | 22.7
|  |  | QA | 2 | 0 | 0
|  |  | Total |  |  | 48.7
|  |  |  | Days | Months
|  |  | Total Effort | 190.2 | 9.51
|  |  | Delivery | 86.625 | 4.3312
vvvcnmnmvbn

## Mobile
Sportlr 24 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1 | 55 | 55
Modules |  |  |  |  | iOS Developer | 1 | 56.75 | 56.75
Register | 8 | 1 | 8 | 1 | QA | 2 | 14.875 | 29.75
Login | 6 | 0.75 | 6 | 0.75 | Total |  |  | 141.5
Remember me/Forgot password | 6 | 0.75 | 6 | 0.75
Bilingual | 20 | 2.5 | 20 | 2.5 | Delivery Time | 71.625
Search | 16 | 2 | 16 | 2 | tottal effort | 141.5
Listing of the category | 16 | 2 | 16 | 2
Details of category | 20 | 2.5 | 20 | 2.5
score displaying | 16 | 2 | 16 | 2
Games based on each date | 20 | 2.5 | 20 | 2.5
Displaying todays match | 10 | 1.25 | 10 | 1.25
most watched list | 10 | 1.25 | 10 | 1.25
side menu | 10 | 1.25 | 10 | 1.25
facebook integration | 20 | 2.5 | 20 | 2.5
twitter integration | 20 | 2.5 | 20 | 2.5
linkedin integration | 20 | 2.5 | 20 | 2.5
nabd integration | 20 | 2.5 | 20 | 2.5
youtube player | 16 | 2 | 16 | 2
telegram | 16 | 2 | 16 | 2
whatsapp | 10 | 1.25 | 10 | 1.25
SQA
QA & Bug fixing | 112 | 14 | 126 | 15.75
UAT | 40 | 5 | 40 | 5
Deployment | 8 | 1 | 8 | 1
| 440 | 55 | 454 | 56.75
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.