## Web
SPORTLR 24 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 35.2 | 4.4 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 4.4 | 4.4
Design and Prototype (mobile & Web) | 64 | 8 | Jr Developer | 1 | 25 | 25 | 49 | 48.5
Development |  |  | Sr Developer | 1 | 24 | 24
Application Basic setup | 8 | 1 | Mobile API | 1 | 22.05 | 22.05
|  |  | QA | 2 | 11.4875 | 22.975
| 6 | 0.75 | Total |  |  | 115.425
| 6 | 0.75
| 6 | 0.75 |  | Days | Months
| 6 | 0.75 | Total Effort | 115.425 | 5.7713
| 6 | 0.75 | Delivery Timeline | 49.4875 | 2.4744
| 6 | 0.75
| 6 | 0.75
| 16 | 2
| 12 | 1.5
| 12 | 1.5
| 12 | 1.5
| 24 | 3
| 8 | 1
| 8 | 1
| 16 | 2
| 24 | 3
| 12 | 1.5
| 12 | 1.5
| 12 | 1.5
| 12 | 1.5
| 12 | 1.5
| 16 | 2
| 16 | 2
| 16 | 2
| 16 | 2
| 12 | 1.5
| 12 | 1.5
| 6 | 0.75
| 16 | 2
0
| 12 | 1.5
| 12 | 1.5
| 12 | 1.5
SQA
QA & Bug fixing | 135.8 | 16.975
UAT | 40 | 5
Deployment | 8 | 1
Total | 743 | 92.875
vvvcnmnmvbn

## Mobile
Sportlr 24 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1 | 33 | 33
[5 empty] | iOS Developer | 1 | 33 | 33
[5 empty] | QA | 1 | 0 | 0
[5 empty] | Total |  |  | 66
Actual purchase is offline
SQA
QA & Bug fixing | 0 | 0 | 0 | 0
UAT |  | 0 |  | 0
Deployment |  | 0 |  | 0
| 0 | 0 | 369.6 | 0
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.