## Web
Tatweer - Asset Managment 29 June 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 99 | 12.375 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 12.375 | 12.375
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 2 | 31 | 62 | 124 | 123.75
Development |  |  | Sr Developer | 2 | 31 | 62
Application Basic setup | 0 | 0 | Mobile API | 1 | 0 | 0
Master Data |  |  | QA | 2 | 27.75 | 55.5
Asset Master | 8 | 1 | Total |  |  | 210.875
Asset Groups | 8 | 1
Asset Locations | 4 | 0.5 |  | Days | Months
Inventory Master | 12 | 1.5 | Total Effort | 210.875 | 10.5437
Part Master with maintenance option | 12 | 1.5 | Delivery Timeline | 73.75 | 3.6875
Drivers | 6 | 0.75
Vehicles | 6 | 0.75
Crew | 6 | 0.75
Asset - Parts Linker | 8 | 1
Suppliers | 6 | 0.75
Job Locations | 4 | 0.5
Inspection check list templates for assets | 12 | 1.5
Scan Barcodes | 0 | 0
Asset Management
Asset Transactions
Purchase Return | 8 | 1
Asset Requisition | 8 | 1
Material Issue | 8 | 1
Material Return | 8 | 1
Location Transfer Out | 8 | 1
Location Transfer In | 8 | 1
Adjustment | 8 | 1
Documents
Goods Receipt | 6 | 0.75
Purchase Return to Supplier | 6 | 0.75
Material Issue | 6 | 0.75
Material Return | 6 | 0.75
Location Transfer Out | 6 | 0.75
Location Transfer In | 6 | 0.75
Reports (Export to PDF & Excel)
Stock Movement by location | 8 | 1
Stock unconfirmed | 8 | 1
Daily Store Movement | 6 | 0.75
Inventory transfer Out | 6 | 0.75
Inventory Transfer In | 6 | 0.75
Stock Ledger | 6 | 0.75
Delivery by Vehicle & Driver | 6 | 0.75
Issued Items in a period | 6 | 0.75
All Assets | 6 | 0.75
Utilities
Import Assets | 8 | 1
Import Parts | 4 | 0.5
Import Suppliers | 4 | 0.5
Import Inventory | 4 | 0.5
Program Management
Create Job | 8 | 1
Create Tasks in Job | 8 | 1
Create Sub Tasks | 16 | 2
Schedule Tasks | 12 | 1.5
Assign Crew to tasks | 12 | 1.5
Assign Location to tasks | 12 | 1.5
Link Assets to to Tasks | 12 | 1.5
Progress update by Sub tasks, Tasks and Job (manual) | 12 | 1.5
Update tickets automatically(If needed) | 12 | 1.5
Capture Evidence & Signoff job completion | 12 | 1.5
Trigger Maintenance jobs for task completions | 12 | 1.5
Trigger Inspection Activities | 12 | 1.5
Asset Maintanance & Inspections
Create Inspection Schedules (Linked to Maintenance job Triggers) | 16 | 2
Prepopulate Schedule with Location, Parts, manufacturer reccomended maintainance window & check lists | 12 | 1.5
Create tasks for schedule | 12 | 1.5
Create schedule check list from template or create new | 12 | 1.5
Assign Crew to tasks | 6 | 0.75
Update Tasks | 6 | 0.75
Requisition Assets for damages found | 6 | 0.75
Create Tickets for damages | 12 | 1.5
Ticketing
Update ticket status | 8 | 1
Assign Ticket owner | 8 | 1
Create Job for ticket (Linked to program management) | 6 | 0.75
Resolve Ticket | 6 | 0.75
Dashboards
Interactive Map View with job locations | 40 | 5
Tasks Completed |  | 0
Crew deployed |  | 0
Parts Deployed |  | 0
Overall completion status |  | 0
Impediments found |  | 0
Near realtime view of crew movement (assuming the crew carries a mobile device with app installed) |  | 0
Installation Schedules | 12 | 1.5
Inspection Schedules | 12 | 1.5
Maintennace Schedules | 12 | 1.5
Installation staus by job | 6 | 0.75
Inspection status by job | 6 | 0.75
Maintennace status by job | 6 | 0.75
Ticketing status | 6 | 0.75
Crew deployments | 6 | 0.75
Impediments by Job | 6 | 0.75
Other KPIs (6 hrs per KPI) | 6 | 0.75
Asset returns / surplus / defects | 6 | 0.75 | Note: 6 hrs / KPI
Assets linked to jobs | 6 | 0.75
Actual vs Planned scheduled by job | 6 | 0.75
System Integrations
Single Sign On | 8 | 1
Multi Factor Authentication | 8 | 1
AMS integration | 24 | 3
MMIS Integration | 24 | 3
SMS Gateway integration | 16 | 2
Document management | 24 | 3
Data Archival | 16 | 2 |  | data encryption
Map integration | 40 | 5
ELK Integration | 0 | 0 | 40
Minio Integration | 0 | 0 | 32
Redis Integration | 8 | 1
Security
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
System Features
Authentication, Authorization, Roles | 24 | 3
Exception Handling and Error logging | 16 | 2
Auditing & Logging | 16 | 2
Search Engine | 24 | 3
Notification management | 24 | 3
Reporting Engine | 16 | 2
Workflow management | 24 | 3
Mobile API
Mobile API | 0 | 0
SQA
QA & Bug fixing | 396 | 49.5
UAT | 40 | 5
Deployment | 8 | 1
Total | 1685 | 210.625
210.625

## Mobile
Tatweer - Asset Managment 29 June 2020
Module | Hours | Man Days | Resources | Utilization
Development
Splash Screen
Application Setup
UI Design by developer
Crew
Todays Schedule
Job Assigned
Task and task details in job
Item checklist
Accept Task
Update task
Capture evidence (upload images, video, documents, audio)
Navgate to job
Update GPS location
Create impediments
Create Schedule delays
Create notes
Update Job Status
Report issues
Supervisor
View Active Job Locations
Track crew assigned to jobs
Track Job status / task Status
Track crew location
Track impediments
Scan Barcodes
Update GPS location
Navigate to Job location
Create Schedule delays caused by impediments
Upload multimedia to document job status and progress
link to asset management
link to maintenance management
View Inspection Schedules & Status
View inspection Check list
Update inspection results and upload evidence (images, video, audio, text)
View Tickets, Ticket details & Status
Create & Update tickets
Update Job Status & task status
Report Crew
Common Features
Login / logout
Update preferences
Update account details
SQA
QA & Bug fixing
UAT
Deployment