## Web
Tatweer - Asset Managment 29 June 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 99 | 12.375 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 12.375 | 12.375
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 2 | 31 | 62 | 124 | 123.75
Development |  |  | Sr Developer | 2 | 31 | 62
Application Basic setup | 0 | 0 | Mobile API | 1 | 14.7375 | 14.7375
Master Data |  |  | QA | 2 | 30.6975 | 61.395
Asset Master | 8 | 1 | Total |  |  | 231.5075
Asset Groups | 8 | 1
Asset Locations | 4 | 0.5 |  | Days | Months
Inventory Master | 12 | 1.5 | Total Effort | 231.5075 | 11.5754
Part Master with maintenance option | 12 | 1.5 | Delivery Timeline | 76.6975 | 3.8349
Drivers | 6 | 0.75
Vehicles | 6 | 0.75
Crew | 6 | 0.75
Asset - Parts Linker | 8 | 1
Suppliers | 6 | 0.75
Job Locations | 4 | 0.5
Inspection check list templates for assets | 12 | 1.5
Scan Barcodes | 0 | 0
Asset Management
Asset Transactions
Purchase Return | 8 | 1
Asset Requisition | 8 | 1
Material Issue | 8 | 1
Material Return | 8 | 1
Location Transfer Out | 8 | 1
Location Transfer In | 8 | 1
Adjustment | 8 | 1
Documents
Goods Receipt | 6 | 0.75
Purchase Return to Supplier | 6 | 0.75
Material Issue | 6 | 0.75
Material Return | 6 | 0.75
Location Transfer Out | 6 | 0.75
Location Transfer In | 6 | 0.75
Reports (Export to PDF & Excel)
Stock Movement by location | 8 | 1
Stock unconfirmed | 8 | 1
Daily Store Movement | 6 | 0.75
Inventory transfer Out | 6 | 0.75
Inventory Transfer In | 6 | 0.75
Stock Ledger | 6 | 0.75
Delivery by Vehicle & Driver | 6 | 0.75
Issued Items in a period | 6 | 0.75
All Assets | 6 | 0.75
Utilities
Import Assets | 8 | 1
Import Parts | 4 | 0.5
Import Suppliers | 4 | 0.5
Import Inventory | 4 | 0.5
Program Management
Create Job | 8 | 1
Create Tasks in Job | 8 | 1
Create Sub Tasks | 16 | 2
Schedule Tasks | 12 | 1.5
Assign Crew to tasks | 12 | 1.5
Assign Location to tasks | 12 | 1.5
Link Assets to to Tasks | 12 | 1.5
Progress update by Sub tasks, Tasks and Job (manual) | 12 | 1.5
Update tickets automatically(If needed) | 12 | 1.5
Capture Evidence & Signoff job completion | 12 | 1.5
Trigger Maintenance jobs for task completions | 12 | 1.5
Trigger Inspection Activities | 12 | 1.5
Asset Maintanance & Inspections
Create Inspection Schedules (Linked to Maintenance job Triggers) | 16 | 2
Prepopulate Schedule with Location, Parts, manufacturer reccomended maintainance window & check lists | 12 | 1.5
Create tasks for schedule | 12 | 1.5
Create schedule check list from template or create new | 12 | 1.5
Assign Crew to tasks | 6 | 0.75
Update Tasks | 6 | 0.75
Requisition Assets for damages found | 6 | 0.75
Create Tickets for damages | 12 | 1.5
Ticketing
Update ticket status | 8 | 1
Assign Ticket owner | 8 | 1
Create Job for ticket (Linked to program management) | 6 | 0.75
Resolve Ticket | 6 | 0.75
Dashboards
Interactive Map View with job locations | 40 | 5
Tasks Completed |  | 0
Crew deployed |  | 0
Parts Deployed |  | 0
Overall completion status |  | 0
Impediments found |  | 0
Near realtime view of crew movement (assuming the crew carries a mobile device with app installed) |  | 0
Installation Schedules | 12 | 1.5
Inspection Schedules | 12 | 1.5
Maintennace Schedules | 12 | 1.5
Installation staus by job | 6 | 0.75
Inspection status by job | 6 | 0.75
Maintennace status by job | 6 | 0.75
Ticketing status | 6 | 0.75
Crew deployments | 6 | 0.75
Impediments by Job | 6 | 0.75
Other KPIs (6 hrs per KPI) | 6 | 0.75
Asset returns / surplus / defects | 6 | 0.75 | Note: 6 hrs / KPI
Assets linked to jobs | 6 | 0.75
Actual vs Planned scheduled by job | 6 | 0.75
System Integrations
Single Sign On | 8 | 1
Multi Factor Authentication | 8 | 1
AMS integration | 24 | 3
MMIS Integration | 24 | 3
SMS Gateway integration | 16 | 2
Document management | 24 | 3
Data Archival | 16 | 2 |  | data encryption
Map integration | 40 | 5
ELK Integration | 0 | 0 | 40
Minio Integration | 0 | 0 | 32
Redis Integration | 8 | 1
Security
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
System Features
Authentication, Authorization, Roles | 24 | 3
Exception Handling and Error logging | 16 | 2
Auditing & Logging | 16 | 2
Search Engine | 24 | 3
Notification management | 24 | 3
Reporting Engine | 16 | 2
Workflow management | 24 | 3
Mobile API
Mobile API | 117.9 | 14.7375
SQA
QA & Bug fixing | 443.16 | 55.395
UAT | 40 | 5
Deployment | 8 | 1
Total | 1850.06 | 231.2575
231.2575

## Mobile
Tatweer - Asset Managment 29 June 2020
Module | Hours | Man Days | Hours | Man Days | Resources | # | Days | Total
Development | Android |  | iOS |  | Jr. Developer | 1 | 18 | 18 | 35 | 34.75
Splash Screen | 8 | 1 | 8 | 1 | Sr. Developer | 1 | 17 | 17
Application Setup | 8 | 1 | 8 | 1 | QA | 1 | 21.6375 | 21.6375
UI Design by developer |  | 0 |  | 0 | Total |  |  | 56.6375
Crew
Todays Schedule | 6 | 0.75 | 6 | 0.75 | Total Effort | 56.6375
Job Assigned | 6 | 0.75 | 6 | 0.75 | Delivery Time | 39.6375 | per track
Task and task details in job | 6 | 0.75 | 6 | 0.75
Item checklist | 6 | 0.75 | 6 | 0.75
Accept Task | 6 | 0.75 | 6 | 0.75
Update task | 8 | 1 | 8 | 1
Capture evidence (upload images, video, documents, audio) | 16 | 2 | 16 | 2
Navgate to job | 8 | 1 | 8 | 1
Update GPS location | 6 | 0.75 | 6 | 0.75
Create impediments | 8 | 1 | 8 | 1
Create Schedule delays | 8 | 1 | 8 | 1
Create notes | 6 | 0.75 | 6 | 0.75
Update Job Status | 6 | 0.75 | 6 | 0.75
Report issues | 6 | 0.75 | 6 | 0.75
Supervisor
View Active Job Locations | 4 | 0.5 | 4 | 0.5
Track crew assigned to jobs | 6 | 0.75 | 6 | 0.75
Track Job status / task Status | 6 | 0.75 | 6 | 0.75
Track crew location | 6 | 0.75 | 6 | 0.75
Track impediments | 6 | 0.75 | 6 | 0.75
Scan Barcodes | 10 | 1.25 | 10 | 1.25
Update GPS location | 8 | 1 | 8 | 1
Navigate to Job location | 6 | 0.75 | 6 | 0.75
Create Schedule delays caused by impediments | 8 | 1 | 8 | 1
Upload multimedia to document job status and progress | 8 | 1 | 8 | 1
link to asset management | 8 | 1 | 8 | 1
link to maintenance management | 8 | 1 | 8 | 1
View Inspection Schedules & Status | 6 | 0.75 | 6 | 0.75
View inspection Check list | 6 | 0.75 | 6 | 0.75
Update inspection results and upload evidence (images, video, audio, text) | 10 | 1.25 | 10 | 1.25
View Tickets, Ticket details & Status | 8 | 1 | 8 | 1
Create & Update tickets | 8 | 1 | 8 | 1
Update Job Status & task status | 8 | 1 | 8 | 1
Report Crew | 8 | 1 | 8 | 1
Common Features
Login / logout | 8 | 1 | 8 | 1
Update preferences | 6 | 0.75 | 6 | 0.75
Update account details | 8 | 1 | 8 | 1
SQA
QA & Bug fixing | 125.1 | 15.6375 | 125.1 | 15.6375
UAT | 40 | 5 | 40 | 5
Deployment | 8 | 1 | 8 | 1
Total | 451.1 | 56.3875 | 451.1 | 56.3875
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.