## Sheet1
Sno | Page | Status | Comment
1 | signup | Completed
2 | signin | Completed
3 | set-password | Not Needed
4 | index | Not Done | HTML Not Completed
5 | qrc-request-management | In Progress | Angular Controls finished, design issues to be fixed by Sharath
6 | user-content-list | In Progress | Angular Controls finished, design issues to be fixed by Sharath
7 | make-profile | In Progress | Angular Controls finished, design issues to be fixed by Sharath
8 | create-test | Completed | Top banner to be provided
9 | take-test | Completed | Top banner to be provided
10 | resources | In Progress | Angular Controls finished, design issues to be fixed by Sharath
11 | resource-details | In Progress | Angular Controls finished, design issues to be fixed by Sharath
12 | dashboard | In Progress | Angular Controls finished, design issues to be fixed by Sharath
13 | create-resource | In Progress | Angular Controls finished, design issues to be fixed by Sharath
14 | create-course | In Progress | Angular Controls finished, design issues to be fixed by Sharath
15 | courses | In Progress | Angular Controls finished, design issues to be fixed by Sharath
16 | course-details | In Progress | Angular Controls finished, design issues to be fixed by Sharath
1 | Header | In Progress | Angular Controls finished, design issues to be fixed by Sharath
2 | Footer | Completed | Done, links to be provided
3 | Top Banner | In Progress | Done for which HTML is done
4 | Jquery to Javascript for responsive design | Not started | Has to be given by Sharath
All the pages are pushed in the Repository