## OER
UAE-OER |  | Sep 29 2018
Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 32 | 4 | Designer | 1 | 80 | 10 | 10
Functional Specification | 32 | 4 | Web Developer | 1 | 500 | 62.5 | 62.5 | 5 | 113.5
Project Management | 4 | 0.5 | sr. developer | 1 | 408 | 51 | 51
Graphic Design | 80 | 10 | PM | 1 | 68 | 8.5 | 8.5
Working Prototype | 0 | 0 | QA | 2 | 8 | 1 | 2
Development |  |  | Total |  | 1064 |  | 134 | 1072
Courses
Create course through proposal process |  |  | Total Delivery days | 73.5
Create a Course through administrative screens |  |  | Total Man day Effort | 134
Define course Key Identification information
Define course description
Define alternate identifiers, cross-listing and version codes
Specify join offerings
Specify key dates and terms
Identify course resources (Faculty)
Identify other course resources
define multiple formats and activities
define course grading and credit options
define learning objectives
define course requisites
define organizational relationships
specify financial information
attach supporting information
attach comments
external wordpress
Only authentication
not in scope
not in scope
not in scope
not in scope
System features
Authentication & authorization |  | 0
Auditing & logging | 40 | 5
Exception handling |  | 0
Manage files and directories |  | 0
Testing & Deployment
Testing | 12 | 1.5
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 212 | 26.5
Assumptions
The application will be a responsive web application
SCORM +IMS LT1 + Open Source integrations not in scope