## WGC
WGC |  | 2019-06-18
Tuesday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | UI / UX | 1 | 3 | 3
System Study | 0 | 0 | Developer | 1 | 37.75 | 37.75 | 0 | 3 | 0 | 3
SRS, FRS, Project Plan, Weekly Status | 22 | 2.75 | PM | 1 | 3.775 | 3.775
Prototype - integrate theme | 24 | 3 | QA | 1 | 15.1 | 15.1
Application Development and Testing |  |  | Tech Writer | 1 | 2.75 | 2.75
|  |  | Total |  |  | 62.375
Application Development - Drupal
Admin |  |  | Deliver Days | 55.85
Manage Admin Users | 6 | 0.75 | Total Effort | 62.375
Manage Registered Users | 6 | 0.75
Manage News | 6 | 0.75
Manage Introduction Video, Legal Information, Introduction/Greeting | 6 | 0.75
Manage Contacts/ Responsible Persons | 8 | 1
Manage Subscription service | 8 | 1
Manage Reports | 15 | 1.875
World Giftedness Center Main Pages
Introduction/Greeting | 1 | 0.125
News | 4 | 0.5
Introduction Video | 8 | 1
Legal Information | 6 | 0.75
Contacts/ Responsible Persons | 4 | 0.5
Journal Area
Issues | 4 | 0.5
Login | 2 | 0.25
Review/Editor/Submission area | 10 | 1.25
Subscription service | 10 | 1.25
Online Course Area
Registration Page | 10 | 1.25
Online courses with interactive elements and videos | 8 | 1
Forums | 6 | 0.75 | Third Party Plugin integration
Course Pages | 6 | 0.75 | External package - like PHP BB
Information page on Offline Workshops | 12 | 1.5
Educational Short Films Section | 10 | 1.25
Best Practices Area |  |  | Third Party Plugin integration
Registration Page | 2 | 0.25
Short educational films | 2 | 0.25
Online courses | 1 | 0.125
Forums | 0 | 0
Course Pages | 0 | 0
Newsletter | 4 | 0.5
Award Area
Nomination Entry page | 10 | 1.25
News page | 1 | 0.125
Accreditation Area
Databank with Search Function | 12 | 1.5
Global Map | 14 | 1.75
Others
Global Mentoring Hub (external System) | 0 | 0
Webinar channels | 60 | 7.5 | Controls go to external system
Auto completion | 40 | 5
Quality Assurance
QA & Bug Fixing | 120.8 | 15.1
PM | 30.2 | 3.775
Total Effort | 499 | 62.375
Assumptions
Client need to purchase the theme
Need clarification
Navigation bar is always accessible
Journal Area
Online submission form for authors to submit manuscripts with metadata
ntegrated email system (linked to a e.g. Postfix server) coordinating the entire process of manuscript review amongst authors, editors and reviewers
Customizable interface in general, where parameters can be set by the administrators
Online Courses Area
Possibility to change playback speed of video
mobile app for online courses
Based on the final product concept, additions and changes must be taken into account
Search Function
Results should be delivered in under 2 seconds
Facetted search (i.e. categories)
Access to Global Mentoring Hub site content - Need to provide API
Provide content, which is indexable by elastic search