## Web
| E-commerce |  | 29/4/2020
Wednesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 1.5 | 1.5
1 | Business analysis | 16 | 2 | Sr Developer | 1 | 4 | 4 | 17.25 | 19.725 | 17.25 | 18
2 | Project Management | 13.8 | 1.725 | Jr Developer | 1 | 14 | 14
3 | SRS,FS,User Manual | 8 | 1 | PM | 1 | 1.725 | 1.725
4 | Design and Prototype | 12 | 1.5 | BA | 1 | 2 | 2
| Development |  |  | Tech writer | 1 | 1 | 1
5 | Application basic setup | 8 | 1 | QA | 1 | 8.0375 | 8.0375
| Web Application |  |  | Total | 7 | 32.2625 | 32.2625
| Home Page | 8 | 1
| About Us | 4 | 0.5 | Effort | 32.2625 | + 1 Day (Deployment)
| Register,Login/Logout | 8 | 1 | Delivery Time | 25.5375 | + 1 Day (Deployment)
| Products | 40 | 5
| Add to Cart |  | 0
| Buy Now |  | 0
| Add quantity |  | 0
| Enter details User name,Email, Delivery Address, Phone no |  | 0
| Pay(Payment Integration) |  | 0
| Enquiry Form | 6 | 0.75
| Location | 4 | 0.5
| Contact Us | 4 | 0.5
0
Admin/Backend
| Login/logout | 4 | 0.5
| Dashboard | 8 | 1
| User Management | 8 | 1
| Products (add/edit/delete) | 24 | 3
| Categories and sub-categories |  | 0
| product name,Product price,discount,description |  | 0
| Affiliates |  | 0
| Cheque,credit/debit cards, E-wallet |  | 0
| Add Discounts,coupons &Special offers |  | 0
| Export reports | 6 | 0.75
| Download as PDF, excel files | 6 | 0.75
Quality Assurance
| QA & Bug Fixing | 48.3 | 6.0375
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort |  | 32.5125
Assumptions
The effort may change after a detailed system study

## mobile
E-commerce |  |  |  | 29/4/2020
Wednesday
Module | Android |  | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 | 0 | 0
UI/UX design | 16 | 2 |  |  | Jr Mobile Dev | 1 | 13 | 13 | 17.5 | 18 | 17.5 | 18
Development |  |  |  |  | Sr. Mobile Dev | 1 | 5 | 5
Application Basic Setup | 8 | 1 | 8 | 1 | QA | 1 | 8.125 | 8.125
[5 empty] | Total | 4 | 26.125 | 26.125
Splash Screen | 8 | 1 | 8 | 1
Home Page | 16 | 2 | 16 | 2 | Effort | 26.125 | + 1 Day (Deployment)
About Us | 8 | 1 | 8 | 1 | Delivery Time | 21.125 | + 1 Day (Deployment)
Register,Login/Logout | 16 | 2 | 16 | 2 | API Development | 7.875
Products | 12 | 1.5 | 12 | 1.5 | UI/UX developmet | 2
Multicurrency (Select) | 6 | 0.75 | 6 | 0.75
Add to Cart | 12 | 1.5 | 12 | 1.5
Buy Now | 6 | 0.75 | 6 | 0.75 |  | Man Days
Add quantity | 8 | 1 | 8 | 1 | Total Mobile effort Est. | 62.125
Enter details User name,Email, Delivery Address, Phone no | 8 | 1 | 8 | 1 | Mobile App Dely. | 21.125
Pay(Payment Integration) | 8 | 1 | 8 | 1
Enquiry Form | 6 | 0.75 | 6 | 0.75
Location | 6 | 0.75 | 6 | 0.75
Share | 6 | 0.75 | 6 | 0.75
Contact Us | 6 | 0.75 | 6 | 0.75
API Development
Quality Assurance
QA & Bug Fixing | 49 | 6.125 | 49 | 6.125
UAT | 16 | 2 | 16 | 2
Deployment per instance | 1 | 0.125 | 1 | 0.125
Total Effort | 206 | 25.75 | 206 | 25.75
API Development | 63 | 7.875
Assumptions 1.The estimation may vary with change in design or any features. 2.The estimation is for potrait mode.