## OER
OER-CMS |  | Feb 20 2019
|  | Thursday |  |  |  | 305
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Project documentation | 96 | 12 | Designer | 1 | 176 | 22 | 22
Functional Specification | 40 | 5 | Web Developer | 1.5 | 610 | 76.25 | 114.375 | 228 | 228.75
Project Management | 182.4 | 22.8 | sr. developer | 1.5 | 610 | 76.25 | 114.375
Graphic Design | 96 | 12 | Documentation | 1 | 136 | 17
Working Prototype | 80 | 10 | PM | 1 | 182.4 | 22.8 | 22.8
Development |  |  | QA | 2 | 351.2 | 43.9 | 87.8 | 2890.8
Courses |  |  | Total |  | 2065.6 |  | 361.35
Course Creation |  | 0
Create course through proposal process | 8 | 1 | Total Delivery days | 142.15 | 7.1075
Create a Course through administrative screens | 8 | 1 | Total Man day Effort | 361.35
Course Definition |  | 0
Define course Key Identification information | 6 | 0.75
Define course description | 6 | 0.75
Define alternate identifiers, cross-listing and version codes | 6 | 0.75
Specify join offerings | 6 | 0.75
Specify key dates and terms | 6 | 0.75
Identify course resources (Faculty) | 6 | 0.75
Identify other course resources | 6 | 0.75
Define multiple formats and activities | 6 | 0.75
Define course grading and credit options | 6 | 0.75
Define learning objectives | 6 | 0.75
Define course requisites | 6 | 0.75
Define organizational relationships | 6 | 0.75
Specify financial information | 6 | 0.75
Attach supporting information | 6 | 0.75
Attach comments | 6 | 0.75
Course Management |  | 0
Modify course through proposal process | 6 | 0.75
Modify course through administrative screens | 6 | 0.75
Retire a course | 6 | 0.75
Course Versioning |  | 0
Version course as a result of modification | 6 | 0.75
Prevent versioning because of modification | 6 | 0.75
Activate an approved course version | 6 | 0.75
Ability to publish approved course version in centralized catalog | 6 | 0.75
Course Search |  | 0
Browse catalog for course by subject area or organization | 6 | 0.75
Browse catalog for course using other attributes | 6 | 0.75
Ability to search for coarse | 6 | 0.75
View a course | 6 | 0.75
Select multiple views of course | 6 | 0.75
View version history of course | 6 | 0.75
Ability to print course | 6 | 0.75
Ability to export course to multiple formats | 6 | 0.75
Programs |  | 0
Create Program | 6 | 0.75
Create program through proposal process | 6 | 0.75
Create a program through administrative screens | 6 | 0.75
Program Defenition |  | 0
Specify key program identification | 6 | 0.75
Specify program description | 6 | 0.75
Specify program dates and terms | 6 | 0.75
Identify program resources - faculty | 6 | 0.75
Define program learning objectives | 6 | 0.75
Ability to define Program Entrance, Satisfactory Progress and Completion Requirements | 6 | 0.75
Ability to specify Organizational Relationships | 6 | 0.75
Manage Program |  | 0
Ability to modify a Program through a proposal process | 6 | 0.75
Ability to modify a Program through administrative screens | 6 | 0.75
Ability to retire a Program through a proposal process | 6 | 0.75
Ability to retire a Program through administrative screens | 6 | 0.75
Program Versioning |  | 0
Ability to version a Program as a result of a modification | 6 | 0.75
Ability not to version a Program as a result of a modification | 6 | 0.75
Ability to activate an approved Program version | 6 | 0.75
Program Publishing |  | 0
Ability to publish approved Program versions in a centralized catalog | 6 | 0.75
Ability to designate other publishing targets (i.e., not the catalog) | 6 | 0.75
Ability to define information to be published by target | 6 | 0.75
Browse and search programs |  | 0
Ability to browse the catalog for a Program | 6 | 0.75
Ability to search for a Program | 6 | 0.75
Ability to view a Program | 6 | 0.75
Ability to view the version history of a Program | 6 | 0.75
Ability to print details of a Program | 6 | 0.75
Ability to export details of a Program | 6 | 0.75
Proposals |  | 0
Start Proposals |  | 0
Ability to start a Proposal to create a Course from blank | 6 | 0.75
Ability to start a Proposal to create a Course from a copy of an another approved Course | 6 | 0.75
Ability to start a Proposal to create a Course from a copy of an another proposed Course | 6 | 0.75
Ability to start a Proposal to create a Course from a template | 6 | 0.75
Ability to start a Proposal to modify a Course from a copy of the Course | 6 | 0.75
Ability to start a Proposal to modify a Program from a copy of the Program | 6 | 0.75
Ability to save and return to a Proposal | 6 | 0.75
Ability to cancel a Proposal | 6 | 0.75
Proposal Collaboration |  | 0
Ability to attach Supporting Documents to a Proposal | 6 | 0.75
Ability to add Collaborators to View, Comment and/or Edit a Proposal | 6 | 0.75
Ability to notify Collaborators that their participation is requested | 6 | 0.75
Ability to remove Collaborators from a Proposal | 6 | 0.75
Proposal Review |  | 0
Ability to specify a workflow based on Proposal type | 6 | 0.75
Ability to specify a workflow based on Proposal data | 6 | 0.75
Ability to submit a Proposal to workflow | 6 | 0.75
Ability to withdraw a Proposal from workflow | 6 | 0.75
Ability to assign reviewers View, Comment and/or Edit proposal permissions | 6 | 0.75
Ability to Request a Decision from a reviewer | 6 | 0.75
Ability to notify reviewers of a pending review/decision request | 6 | 0.75
Ability of reviewers to Enter a Decision on the proposal | 6 | 0.75
Ability of reviewers to determine the status of a proposal | 6 | 0.75
Ability to view the History of the proposal as it moves through the review process | 6 | 0.75
Ability to record the final Outcome of the review process | 6 | 0.75
Ability to review grouped proposals simultaneously | 6 | 0.75
Ability to group proposals | 6 | 0.75
Archive, Search & View Proposals |  | 0
Ability to archive a proposal | 6 | 0.75
Ability to Search for Proposals | 6 | 0.75
Ability to view a Proposal | 6 | 0.75
Ability to export details of a Program | 6 | 0.75
Ability to print a Proposal | 6 | 0.75
Course Set |  | 0
Create Course Set |  | 0
Ability to create a fixed or dynamic Course Set | 6 | 0.75
Ability to create a single-use and/or reusable Course Set | 6 | 0.75
Ability to create Course Set that contains proposed or approved courses | 6 | 0.75
Ability to create a Course Set that contains courses and/or other Course Sets | 6 | 0.75
Manage Reusable course set |  | 0
Ability to modify reusable Course Sets | 6 | 0.75
Ability to retire reusable Course Sets | 6 | 0.75
Ability to delete reusable Course Sets | 6 | 0.75
Ability to version reusable Course Sets | 6 | 0.75
Learning Objectives |  | 0
Define learning objectives |  | 0
Ability to author Learning Objectives | 6 | 0.75
Ability to edit Learning Objectives | 6 | 0.75
Ability to delete Learning Objectives | 6 | 0.75
Ability to search for, copy and then edit Learning Objectives | 6 | 0.75
Organize Learning Objectives |  | 0
Ability to order Learning Objectives | 6 | 0.75
Ability to create a hierarchy of Learning Objectives with levels and sublevels | 6 | 0.75
Ability to create Learning Objectives categories | 6 | 0.75
Ability to maintain an inventory of Learning Objectives categories | 6 | 0.75
Ability to manage an inventory of Governed Learning Objectives | 6 | 0.75
Ability to categorize Learning Objectives | 6 | 0.75
Attach Learning Objectives |  | 0
Ability to attach Learning Objectives to a Course | 6 | 0.75
Ability to attach Learning Objectives to a Course Activity | 6 | 0.75
Ability to attach Learning Objectives to a Program | 6 | 0.75
Ability to map Program Learning Objectives to Courses that support them | 6 | 0.75
Course Analysis |  | 0
Ability to determine the Dependence of Other Courses on a Selected Course |  | 0
Ability to determine which Courses are Jointly-Offered with the Selected Course | 6 | 0.75
Ability to determine which Courses are Cross-listed with the Selected Course | 6 | 0.75
Ability to determine which Courses use the Selected Course in a Prerequisite Rule | 6 | 0.75
Ability to determine which Courses list the Selected Course in a Corequisite Rule | 6 | 0.75
Ability to determine which Courses list the Selected Course in a Antirequisite Rule | 6 | 0.75
Ability to determine which Courses list the Selected Course as a Recommended Preparation | 6 | 0.75
Ability to determine Oversight Organization(s) of the Dependent Courses | 6 | 0.75
Ability to determine the Dependence of Programs on a Selected Course |  | 0
Ability to determine which Programs list the Selected Course as an Entrance Requirement | 6 | 0.75
Ability to determine which Programs list the Selected Course as a Satisfactory Progress Requirement | 6 | 0.75
Ability to determine which Programs list the Selected Course as a Completion Requirement | 6 | 0.75
Ability to determine Oversight Organization(s) of the Dependent Programs | 6 | 0.75
Ability to determine the membership of a Selected Course in Reusable Course Sets |  | 0
Ability to determine which Reusable Fixed Course Sets contain the Selected Course | 6 | 0.75
Ability to determine which Reusable Dynamic Course Sets contain the Selected Course | 6 | 0.75
Ability to determine Oversight Organization(s) of the Dependent Course Sets | 6 | 0.75
Ability to access details of the Dependencies |  | 0
Ability to filter the the analysis results | 6 | 0.75
Ability to view the Dependent Course from the analysis results | 6 | 0.75
Ability to view the Dependent Program from the analysis results | 6 | 0.75
Ability to view the Dependent Course Set from the analysis results | 6 | 0.75
Program Analysis |  | 0
Ability to view which Courses are shared across two or more Selected Programs | 6 | 0.75
Ability to run an analysis of a Select Program based on Learning Objectives | 6 | 0.75
Ability to determine the Prerequisite chains for required Courses in a Selected Program | 6 | 0.75
Ability to view which Courses associated with the Selected Program are not owned by the same Oversight Organization as the Selected Program | 6 | 0.75
Other |  | 0
Ability to print the results of a Dependency Analysis | 6 | 0.75
Ability to export the results of a Dependency Analysis | 6 | 0.75
Ability to automatically trigger a Dependency Analysis as part of a Modify or Retire Course Proposal | 6 | 0.75
Ability to send notifications to Oversight Organization(s) of Dependent Courses, Course Sets, and Programs | 6 | 0.75
Backend Services |  | 0
Academic Time Period Service | 16 | 2
Canonical Learning Unit Service | 16 | 2
Comment service | 16 | 2
Course Service | 16 | 2
Document service | 16 | 2
Enumeration Management Service | 16 | 2
Learning Objective Service | 16 | 2
Dictionary Service | 16 | 2
Learning Result Catalog Service | 16 | 2
Message Service | 16 | 2
Organization Service | 16 | 2
Program Service | 16 | 2
Proposal service | 16 | 2
Search Service | 16 | 2
State Service | 16 | 2
Statement Service | 16 | 2
Type Service | 16 | 2
Version Management Service | 16 | 2
Configurations |  | 0
Institutions | 16 | 2
User initerface | 16 | 2
Themes | 16 | 2
Layout, Views, sections & fields | 16 | 2
Messages, labels & help text | 12 | 1.5
Service dictionaries | 12 | 1.5
Searches, pickers and browsers (eg. Catalog browser) | 12 | 1.5
Rules, Enumerations, field bindings | 12 | 1.5
Business processes and workflows | 12 | 1.5
Accreditization |  | 0
Accreditization application | 12 | 1.5
Results of initial or preliminary visit | 12 | 1.5
Approval results of accreditization commision | 12 | 1.5
Address initial visit reccomendation | 12 | 1.5
Self-study results | 12 | 1.5
Full visit result details | 12 | 1.5
Visiting committee report | 12 | 1.5
visiting committee reccomendation accreditization status | 12 | 1.5
Commisions actions on status or conditions | 12 | 1.5
Refinement and submission of schoolwide action plan | 12 | 1.5
Submission of interim progress reports | 12 | 1.5
Subsequent reviews and reaffirmation of accreditization | 12 | 1.5
Systematic improvement and renewal | 12 | 1.5
Misc |  | 0
Single Sign on | 8 | 1
API Integrations | 8 | 1
Bilingual Site | 356 | 44.5
0
System features |  | 0
Authentication & authorization | 16 | 2
Auditing & logging | 16 | 2
Exception handling | 16 | 2
Manage files and directories | 16 | 2
Testing & Deployment |  | 0
Testing | 638.4 | 79.8
UAT | 40 | 5
Deployment | 24 | 3
Total Effort | 3020.8 | 377.6
Assumptions
The application will be a responsive web application
SCORM +IMS LT1 + Open Source integrations not in scope