## Ecommerce
| HIRA Ecommerce Web Application |  | 2019-05-27
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 0 | 0 | 0
1 | Business analysis | 8 | 1 | Sr Developer | 1 | 9 | 9 | 7 | 9.8 | 9
2 | Project Management | 6.4 | 0.8 | Jr Developer | 0 | 0 | 0
3 | SRS,FS,User Manual,Weekly Report | 48 | 6 | PM | 1 | 0.8 | 0.8
| Development | 64 | 8 | BA | 1 | 1 | 1
4 | Creating Developemt Environment PHP - Opencart |  |  | Tech writer | 1 | 6 | 6
5 | Theme Integration & Configuration |  |  | QA | 2 | 2.1 | 4.2
| Web Module | 56 | 7 | Total | 6 | 18.9 | 21
6 | Responsive Design
7 | User Registration |  |  | Effort | 21 | + 1 Day (Deployment)
8 | Authentication and Authorization |  |  | Delivery Time | 9.9 | + 1 Day (Deployment)
9 | Related products, suggestions & wish list
10 | Shopping cart
11 | Product Comments and ratings
12 | Unlimited product categories, products and manufacturers
13 | Intelligent product search with filters
14 | Integration with payment gateway
15 | Promotions and special offers
16 | Social media integration
Admin
17 | Add new Categories and Products (Product uploads)
18 | Create discounts for customers (special offers & discounts)
19 | Analytics, event notification system and reporting
20 | Manage Site content
21 | Manage user groups, User & Roles ( Site admins, Store managers)
22 | Manage Stock, Orders, Returns & Prices
| Additional Features | 8 | 1
23 | Product Enquiry Form [Extension]
Quality Assurance
24 | QA & Bug Fixing | 25.6 | 3.2
25 | UAT | 8 | 1
26 | Deployment per instance | 8 | 1
| Total Effort | 168 | 21
Assumptions
Open Cart theme & Extension need to be purchased
Open cart theme estimate price: $65
Extension estimate price: $20
Out of Scope
Data Entry
Customization of theme will be extra effort.