## Web
Online Auction Platform 22 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 93.2 | 11.65 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 11.65 | 11.65
Design and Prototype (mobile & Web) | 64 | 8 | Jr Developer | 1 | 62 | 62 | 124 | 124.75
Development |  |  | Sr Developer | 1 | 62 | 62
Application Basic setup | 8 | 1 | Mobile API | 1 | 37.2 | 37.2
Bidder |  |  | QA | 2 | 24.8313 | 49.6625
SignUp / forgot password / remember password | 8 | 1 | Total |  |  | 239.5125
Enter personal data and identification | 6 | 0.75
e-mail Verification | 4 | 0.5 |  | Days | Months
Create ID and password | 4 | 0.5 | Total Effort | 239.5125 | 11.9756
logged-in user |  | 0 | Delivery Timeline | 99.8312 | 4.9916
Dashboard | 16 | 2
Subscribe Auction | 6 | 0.75
Browse items on auction | 16 | 2
Search/Sort | 16 | 2
Agree terms and conditions | 8 | 1
Pay security Deposit | 8 | 1
Add lots | 6 | 0.75
Request deposit Refund(unwinning) | 6 | 0.75
Request viewing appointment | 6 | 0.75
Pay Bid amount(within 48 hrs after auction) | 8 | 1
Increment bid(during auction interval) | 12 | 1.5
Track items concurring to bid | 20 | 2.5
Wallet | 12 | 1.5
Watchlist, Add to watchlist | 8 | 1
View My bids, My Purchases, Results | 12 | 1.5
Add request, view status of the requests | 12 | 1.5
Live Chat | 40 | 5 | Using Twillio. Must pay for subscription depending on usage (simple chat features)
View Profile details | 6 | 0.75
Seller
SignUp | 2 | 0.25
Enter personal data and identification | 8 | 1
Select type(government body/banks/courts/insurance/private entity/individuals) | 8 | 1
Verification | 6 | 0.75
Receive login credentials | 6 | 0.75
Login/Logout |  | 0
Raise request | 12 | 1.5
Assign starting price and conditions | 12 | 1.5
Sign auction agreement | 6 | 0.75
Request asset move to auction place | 8 | 1
Track items concurring to bid | 20 | 2.5
Approve and award winner | 8 | 1
Document and ownership transfer to winner | 12 | 1.5
view history | 6 | 0.75
Monitor live bids | 16 | 2
Administrator
Login/Logout | 2 | 0.25
Dashboard | 24 | 3
Add home page wedges/Categories | 8 | 1
Assign time to receive asset | 12 | 1.5
Facilitate transfer and prepare logistics | 12 | 1.5
Send request to Inspect asset if its machinery/vehicles | 12 | 1.5
Set/Change commission | 6 | 0.75
Change certain fields | 6 | 0.75
Amount of deposit refund | 6 | 0.75
Set New Categories | 6 | 0.75
Calculation | 8 | 1
Financial Controller
Login/Logout | 2 | 0.25
Receive security deposit from bidders | 12 | 1.5
Provide receipt | 12 | 1.5
load receipt of deposit to the bidder wallet | 12 | 1.5
Add security deposit to bidder wallet | 12 | 1.5
Receive refund request and process it | 12 | 1.5
Set the wallet to zero after refund | 6 | 0.75
Coordinate with payment | 12 | 1.5
Dashboard | 24 | 3
Payment not received confiscate security deposit | 12 | 1.5
Deduct commission | 6 | 0.75
Generate reports on a single user or more users | 8 | 1
Get approval/acceptance by manager | 8 | 1
Support User
Login/Logout | 2 | 0.25
assistance to bidder/seller | 12 | 1.5
Receive request through platform/e-mail with documentation | 16 | 2
Help Desk
Login/Logout | 2 | 0.25
Receive asset listing requests, Add bids | 6 | 0.75
Upload pictures documents, details | 4 | 0.5
Upload Signed agreement | 4 | 0.5
Access all auction information | 6 | 0.75
Search(using mobile/username) | 6 | 0.75
Register/open tickets | 6 | 0.75
View the status of the tickets | 6 | 0.75
Assign the tickets to the specific user to be resolved | 6 | 0.75
Front Desk
Login/Logout | 2 | 0.25
Dashboard(pending requests,new requests, resolved) | 2 | 0.25
Receive asset listing requests,Add/edit/delete bids | 4 | 0.5
Upload pictures documents, details | 2 | 0.25
Upload Signed agreement | 2 | 0.25
Fixing appointment to move asset | 6 | 0.75
List assets(selling price, owner, Starting price, approval) | 6 | 0.75
Asset Inspection | 6 | 0.75
Capture image/upload image, upload documents | 2 | 0.25
Enter details /specification details | 2 | 0.25
Add comments | 2 | 0.25
Submit inspection report | 2 | 0.25
Super User
Login/Logout | 2 | 0.25
Dashboard | 16 | 2
Generate reports | 16 | 2
Review bidder registration & approve/reject | 12 | 1.5
Add/modify/delete listings | 12 | 1.5
User role permissions | 24 | 3
Master data management | 32 | 4
User Management | 24 | 3
Re-Auction on not receiving the payment from bidder on agreed time | 12 | 1.5
Re-Auction if bidders do not agree on highest bid | 12 | 1.5
Manager
Login/Logout | 2 | 0.25
Dashboard |  | 0
Receive requests | 6 | 0.75
Approve/reject | 6 | 0.75
Other requirements
Generate Lot no on request | 8 | 1
Payment Integration | 16 | 2
Home Page/Anonymous User
About Us | 4 | 0.5
Contact Us | 4 | 0.5
FAQ | 6 | 0.75
New User Registration | 8 | 1
Login(Registered User) | 4 | 0.5
Live Chat | 16 | 2
Auctions(Active bids) |  | 0
Ongoing auctions with time | 8 | 1
Start/minimum price | 4 | 0.5
current price | 4 | 0.5
List view details and search | 8 | 1
SQA
QA & Bug fixing | 349.3 | 43.6625
UAT | 40 | 5
Deployment | 8 | 1
Total | 1624.5 | 203.0625
vvvcnmnmvbn

## Mobile
Online Auction Platform 22 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1 | 33 | 33
Bidder |  |  |  |  | iOS Developer | 1 | 33 | 33
SignUp | 8 | 1 | 8 | 1 | QA | 1 | 17.675 | 17.675
Enter personal data and identification | 6 | 0.75 | 6 | 0.75 | Total |  |  | 83.675
Verification | 4 | 0.5 | 4 | 0.5
Create ID and password | 6 | 0.75 | 6 | 0.75
Login/Logout | 8 | 1 | 8 | 1
Dashboard
Subscribe Auction
look at items on auction | 6 | 0.75 | 6 | 0.75
Search/Sort | 6 | 0.75 | 6 | 0.75
Agree terms and conditions | 4 | 0.5 | 4 | 0.5
Payment gateway | 24 | 3 | 24 | 3
Pay security Deposit | 8 | 1 | 8 | 1
Add lots | 8 | 1 | 8 | 1
Request deposit Refund(unwinning) | 6 | 0.75 | 6 | 0.75
Request viewing appointment | 6 | 0.75 | 6 | 0.75
Pay Bid amount(within 48 hrs after auction) | 10 | 1.25 | 10 | 1.25
Track items concurring to bid | 10 | 1.25 | 10 | 1.25
Wallet | 6 | 0.75 | 6 | 0.75
Increment bid(during auction interval) | 6 | 0.75 | 6 | 0.75
Watchlist, Add to watchlist
View My bids, My Purchases, Results
Add request, view status of the requests
Live Chat
View Profile details
Seller
SignUp |  | 0 |  | 0
Enter personal data and identification | 8 | 1 | 8 | 1
Select type(government body/banks/courts/insurance/private entity/individuals) | 6 | 0.75 | 6 | 0.75
Verification | 4 | 0.5 | 4 | 0.5
Receive login credentials | 6 | 0.75 | 6 | 0.75
Login/Logout | 8 | 1 | 8 | 1
Raise request | 6 | 0.75 | 6 | 0.75
Assign starting price and conditions | 8 | 1 | 8 | 1
Sign auction agreement | 6 | 0.75 | 6 | 0.75
Request asset move to auction place | 6 | 0.75 | 6 | 0.75
Approve and award winner | 6 | 0.75 | 6 | 0.75
Document and ownership transfer to winner | 6 | 0.75 | 6 | 0.75
Track items concurring to bid | 10 | 1.25 | 10 | 1.25
view history
Monitor live bids
Home Screen
About Us
Contact Us
FAQ
New User Registration
Login(Registered User)
Live Chat
Auctions(Active bids)
Ongoing auctions with time
Start/minimum price
current price
List view details and search | 8 | 1 | 8 | 1
SQA
QA & Bug fixing | 70.7 | 8.8375 | 70.7 | 8.8375
UAT |  | 0 |  | 0
Deployment |  | 0 |  | 0
| 290.7 | 36.3375 | 369.6 | 36.3375
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.