## Web
Online Auction Platform 21 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 54.6 | 6.825 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 6.825 | 6.825
Design and Prototype (mobile & Web) | 64 | 8 | Jr Developer | 1 | 35 | 35 | 69 | 68.25
Development |  |  | Sr Developer | 1 | 34 | 34
Application Basic setup | 8 | 1 | Mobile API | 1 | 27.6 | 27.6
Bidder |  |  | QA | 2 | 14.9437 | 29.8875
SignUp / forgot password / remember password | 8 | 1 | Total |  |  | 150.3125
Subscribe Auction |  | 0
Enter personal data and identification | 6 | 0.75 |  | Days | Months
e-mail Verification | 4 | 0.5 | Total Effort | 150.3125 | 7.5156
Create ID and password | 4 | 0.5 | Delivery Timeline | 62.9438 | 3.1472
logged-in user |  | 0
Browse items on auction | 16 | 2
Search/Sort | 16 | 2
Agree terms and conditions | 8 | 1
Pay security Deposit | 8 | 1
Add lots | 6 | 0.75
Request deposit Refund(unwinning) | 6 | 0.75
Request viewing appointment | 6 | 0.75
Pay Bid amount(within 48 hrs after auction) | 8 | 1
Increment bid(during auction interval) | 12 | 1.5
Anonymous User |  | 0
List view details and search | 8 | 1
Seller
SignUp |  | 0
Enter personal data and identification | 8 | 1
Select type(government body/banks/courts/insurance/private entity/individuals) | 8 | 1
Verification | 6 | 0.75
Receive login credentials | 6 | 0.75
Login/Logout |  | 0
Raise request | 12 | 1.5
Assign starting price and conditions | 12 | 1.5
Sign auction agreement | 6 | 0.75
Request asset move to auction place | 8 | 1
Approve and award winner | 8 | 1
Document and ownership transfer to winner | 12 | 1.5
Administrator
Login/Logout |  | 0
Dashboard | 24 | 3
Receive request through platform/e-mail with documentation | 16 | 2
Assign time to receive asset | 12 | 1.5
Facilitate transfer and prepare logistics | 12 | 1.5
Inspect asset if its machinery/vehicles | 12 | 1.5
Review bidder registration & approve/reject | 12 | 1.5
Add/modify/delete listings | 12 | 1.5
User role permissions | 24 | 3
Master data management | 32 | 4
User Management | 24 | 3
Re-Auction on not receiving the payment from bidder on agreed time | 12 | 1.5
Re-Auction if bidders do not agree on highest bid | 12 | 1.5
Financial Controller
Login/Logout |  | 0
Receive security deposit from bidders | 12 | 1.5
Provide receipt | 12 | 1.5
Add security deposit to bidder wallet | 12 | 1.5
Receive refund request and process it | 12 | 1.5
Coordinate with payment | 12 | 1.5
Dashboard | 24 | 3
Payment not received confiscate security deposit | 12 | 1.5
Other requirements
Generate Lot no on request | 8 | 1
assistance to bidder/seller | 12 | 1.5
Payment Integration | 16 | 2
SQA
QA & Bug fixing | 191.1 | 23.8875
UAT | 40 | 5
Deployment | 8 | 1
Total | 975.7 | 121.9625
vvvcnmnmvbn

## Mobile
Online Auction Platform 21 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1 |  | 0
Bidder |  |  |  |  | iOS Developer | 1 |  | 0
SignUp |  |  |  |  | QA | 1 | 0 | 0
Subscribe Auction |  |  |  |  | Total |  |  | 0
Enter personal data and identification
Verification
Create ID and password
Login/Logout
look at items on auction
Search/Sort
Agree terms and conditions
Pay security Deposit
Add lots
Request deposit Refund(unwinning)
Request viewing appointment
Pay Bid amount(within 48 hrs after auction)
Increment bid(during auction interval)
Anonymous User
List view details and search
Seller
SignUp
Enter personal data and identification
Select type(government body/banks/courts/insurance/private entity/individuals)
Verification
Receive login credentials
Login/Logout
Raise request
Assign starting price and conditions
Sign auction agreement
Request asset move to auction place
Approve and award winner
Document and ownership transfer to winner
SQA
QA & Bug fixing
UAT
Deployment
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.