## Sheet 1
Table 1
IOS Application for Construction Project Defect Management
| Sl.No | Components | Hours | Days
| 1 | Initial setup
|  | R&D for Floor plan interaction | 32 | 4
|  | API & DB setup | 32 | 4
|  | Report generation alignment setup | 24 | 3
|  | Charts & Visual setup | 24 | 3
| 2 | Login Page | 4 | 0.5
| 3 | Home Page | 8 | 1
| 4 | Project list page | 12 | 1.5
| 5 | Project details page (Levels) | 6 | 0.75
| 6 | Units list page | 6 | 0.75
| 7 | Floor plan page(UI) | 16 | 2
| 8 | Addition components(Raise Issues)
|  | Touch interaction design in floor plan | 32 | 4
|  | Add observation using Snag tool | 14 | 1.75
|  | Add end date details | 2 | 0.25
|  | Add photos | 2 | 0.25
|  | Add comments to photos | 2 | 0.25
|  | Edit comments details | 4 | 0.5
|  | Track status of assignment | 6 | 0.75
|  | Assign users to observation | 4 | 0.5
| 9 | Interaction components(Resolving Issues)
|  | View open issues in observation flow | 8 | 1
|  | Resolve open issues flow | 8 | 1
| 10 | Reports View
|  | Projects | 16 | 2
|  | Trades | 16 | 2
|  | Trade and project | 16 | 2
|  | Status of project | 16 | 2
|  | Observations per project | 16 | 2
| 11 | Reports format design (Eg. Charts & visuals) | 24 | 3
| 12 | Reports Generation
|  | Export report to PDF & other formats. | 32 | 4
|  | Sync Data with server | 16 | 2
| 13 | Local DB setup
|  | Create Coredata structure to maintain offline handling | 32 | 4
|  | Offline handling of data | 38 | 4.75
| 14 | API
|  | Project list page API | 8 | 1
|  | Project details page (Levels) API | 8 | 1
|  | Units list page API | 8 | 1
|  | Floor plan page(UI) API | 8 | 1
|  | Add Comments, photos, date & observation details API | 16 | 2
|  | Edit comments, date, observation details API | 16 | 2
|  | Status of projects API | 8 | 1
|  | Resolve open issues API | 18 | 2.25
|  | Assigning users API | 8 | 1
|  | View Reports API | 16 | 2
|  | Sync data API | 16 | 2
|  | Offline/Online handling of details API | 16 | 2
76.75