## Kaizen asset management
| Kaizen asset management | March 10 2017 | March 10 2017
|  | Friday | Friday
Sl. No. | Module | Man Hours | Man Days
| Initiation |  |  |  | No | Man hours | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 32 | 4 | Designer | 1 | 40 | 5 | 5
2 | Functional Specification | 32 | 4 | Sr Developer | 2 | 272 | 34 | 68
3 | Project Management | 64 | 8 | Jr Developer | 2 | 128 | 16 | 32
4 |  | 0 |  | PM | 1 | 152 | 19 | 19
5 | Graphic Design | 40 | 5 | QA | 2 | 152 | 19 | 38
| Development |  |  | Total |  |  |  | 162
|  |  |  | Total Delivery days | 70
5 | Floor plan interaction | 48 | 6 | Total Effort | 162
6 | API & DB setup | 32 | 4
8 | Report generation alignment setup | 24 | 3
9 | Charts & Visual setup | 32 | 4
10 | Create Sessions | 0
11 | Login Page | 4 | 0.5
12 | Home Page | 8 | 1
13 | Project list page | 12 | 1.5
14 | Project details page (Levels) | 6 | 0.75
15 | Units list page | 6 | 0.75
16 | Floor plan page(UI) | 16 | 2
17 | Addition components(Raise Issues) | 0
18 | Touch interaction design in floor plan | 32 | 4
19 | Add observation using Snag tool | 14 | 1.75
20 | Add end date details | 6 | 0.75
21 | Add photos | 6 | 0.75
22 | Add comments to photos | 14 | 1.75
23 | Edit comments details | 4 | 0.5
24 | Track status of assignment | 6 | 0.75
| Assign users to observation | 4 | 0.5
| Interaction components(Resolving Issues) | 0
| View open issues in observation flow | 8 | 1
| Resolve open issues flow | 8 | 1
0
| Reports View | 0
| Projects | 16 | 2
| Trades | 16 | 2
28 | Trade and project | 16 | 2
29 | Status of project | 16 | 2
30 | Observations per project | 16 | 2
31 | Reports format design (Eg. Charts & visuals) | 24 | 3
32 | Reports Generation | 0
| Export report to PDF & other formats. | 32 | 4
33 | Sync Data with server | 16 | 2
34 |  | 0
35 | Local DB setup | 0
36 | Create Coredata structure to maintain offline handling | 32 | 4
| Offline handling of data | 40 | 5
37 |  | 0
38 | API | 0
39 | Project list page API | 8 | 1
| Project details page (Levels) API | 8 | 1
40 | Units list page API | 8 | 1
41 | Floor plan page(UI) API | 8 | 1
| Add Comments, photos, date & observation details API | 16 | 2
42 | Edit comments, date, observation details API | 24 | 3
43 | Status of projects API | 8 | 1
44 | Resolve open issues API | 28 | 3.5
45 | Assigning users API | 8 | 1
| View Reports API | 16 | 2
| Sync data API | 16 | 2
| Offline/Online handling of details API | 16 | 2
0
38 | Admin | 0
| Add Master Entries [5 Pages] | 40 | 5
| Log System Activites | 8 | 1
| Login | 4 | 0.5
| Manage Users & Types | 16 | 2
| Reports | 24 | 3
0
| Testing & Deployment | 0
| Testing | 308 | 38.5
| UAT | 40 | 5
| Deployment | 16 | 2
| Total Effort | 1302 | 162.75