## Kaizen asset management
| Kaizen asset management | March 10 2017 | March 10 2017
|  | Friday | Friday
Sl. No. | Module | Man Hours | Man Days
| Initiation |  |  |  | No | Man hours | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 40 | 5 | 5
2 | Functional Specification | 24 | 3 | Sr Developer | 2 | 432 | 27 | 54 | 84.25 | 84
3 | Project Management | 32 | 4 | Jr Developer | 2 | 240 | 15 | 30
4 |  | 0 |  | PM | 1 | 80 | 10 | 10
5 | Graphic Design | 40 | 5 | QA | 2 | 285.6 | 17.85 | 35.7
| Development |  |  | Total |  | 1077.6 |  | 134.7 | 1077.6
|  |  |  | Total Delivery days | 59.85
5 | Floor plan interaction | 40 | 5 | Total Effort | 134.7
6 | API & DB setup | 24 | 3
8 | Report generation alignment setup | 24 | 3
9 | Charts & Visual setup | 24 | 3
10 | Create Sessions | 0
11 | Login Page | 4 | 0.5
12 | Home Page | 8 | 1
13 | Project list page | 12 | 1.5
14 | Project details page (Levels) | 6 | 0.75
15 | Units list page | 6 | 0.75
16 | Floor plan page(UI) | 16 | 2
17 | Addition components(Raise Issues) | 0
18 | Touch interaction design in floor plan | 32 | 4
19 | Add observation using Snag tool | 14 | 1.75
20 | Add end date details | 6 | 0.75
21 | Add photos | 6 | 0.75
22 | Add comments to photos | 14 | 1.75
23 | Edit comments details | 4 | 0.5
24 | Track status of assignment | 6 | 0.75
| Assign users to observation | 4 | 0.5
| Interaction components(Resolving Issues) | 0
| View open issues in observation flow | 8 | 1
| Resolve open issues flow | 8 | 1
0
| Reports View | 0
| Projects | 8 | 1
| Trades | 8 | 1
28 | Trade and project | 8 | 1
29 | Status of project | 8 | 1
30 | Observations per project | 8 | 1
31 | Reports format design (Eg. Charts & visuals) | 24 | 3
32 | Reports Generation | 0
| Export report to PDF & other formats. | 16 | 2
33 | Sync Data with server | 16 | 2
34 |  | 0
35 | Local DB setup | 0
36 | Create Coredata structure to maintain offline handling | 32 | 4
| Offline handling of data | 32 | 4
37 |  | 0
38 | API | 0
39 | Project list page API | 8 | 1
| Project details page (Levels) API | 8 | 1
40 | Units list page API | 8 | 1
41 | Floor plan page(UI) API | 8 | 1
| Add Comments, photos, date & observation details API | 16 | 2
42 | Edit comments, date, observation details API | 16 | 2
43 | Status of projects API | 8 | 1
44 | Resolve open issues API | 28 | 3.5
45 | Assigning users API | 8 | 1
| View Reports API | 16 | 2
| Sync data API | 16 | 2
| Offline/Online handling of details API | 16 | 2
0
38 | Admin | 0
| Add Master Entries [5 Pages] | 40 | 5
| Log System Activites | 8 | 1
| Login | 4 | 0.5
| Manage Users & Types | 16 | 2
| Reports | 24 | 3
0
| Testing & Deployment | 0
| Testing | 269.6 | 33.7
| UAT | 16 | 2
| Deployment | 8 | 1
| Total Effort | 1087.6 | 135.95