## Kaizen asset management
Kaizen asset management | March 10 2017 | March 10 2017
| Friday | Friday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 40 | 5 | 5
Functional Specification | 24 | 3 | Sr Developer | 2 | 432 | 27 | 54 | 84.75 | 84
Project Management | 32 | 4 | Jr Developer | 2 | 240 | 15 | 30
| 0 |  | PM | 1 | 94 | 10 | 10
Graphic Design | 40 | 5 | QA | 2 | 219.4 | 13.7125 | 27.425
Development |  |  | Total |  | 1025.4 |  | 126.425 | 1011.4
|  |  | Total Delivery days | 55.7125
Floor plan interaction | 40 | 5 | Total Man day Effort | 126.425
API & DB setup | 24 | 3
Report generation alignment setup | 24 | 3
Charts & Visual setup | 24 | 3
Create Sessions | 0
Login Page | 4 | 0.5
Home Page | 8 | 1
Project list page | 12 | 1.5
Project details page (Levels) | 6 | 0.75
Units list page | 6 | 0.75
Floor plan page(UI) | 16 | 2
Addition components(Raise Issues) | 0
Touch interaction design in floor plan | 32 | 4
Add observation using Snag tool | 14 | 1.75
Add end date details | 6 | 0.75
Add photos | 6 | 0.75
Add comments to photos | 14 | 1.75
Edit comments details | 4 | 0.5
Track status of assignment | 6 | 0.75
Assign users to observation | 4 | 0.5
Interaction components(Resolving Issues) | 0
View open issues in observation flow | 8 | 1
Resolve open issues flow | 8 | 1
0
Reports View | 0
Projects | 8 | 1
Trades | 8 | 1
Trade and project | 8 | 1
Status of project | 8 | 1
Observations per project | 8 | 1
Reports format design (Eg. Charts & visuals) | 24 | 3
Reports Generation | 0
Export report to PDF & other formats. | 16 | 2
Sync Data with server | 16 | 2
0
Local DB setup | 0
Create Coredata structure to maintain offline handling | 32 | 4
Offline handling of data | 32 | 4
0
API | 0
Project list page API | 8 | 1
Project details page (Levels) API | 8 | 1
Units list page API | 8 | 1
Floor plan page(UI) API | 8 | 1
Add Comments, photos, date & observation details API | 16 | 2
Edit comments, date, observation details API | 16 | 2
Status of projects API | 8 | 1
Resolve open issues API | 32 | 4
Assigning users API | 8 | 1
View Reports API | 16 | 2
Sync data API | 16 | 2
Offline/Online handling of details API | 16 | 2
0
Admin | 0
Add Master Entries [5 Pages] | 40 | 5
Log System Activites | 8 | 1
Login | 4 | 0.5
Manage Users & Types | 16 | 2
Reports | 24 | 3
0
Testing & Deployment | 0
Testing | 203.4 | 25.425
UAT | 16 | 2
Deployment | 8 | 1
Total Effort | 1025.4 | 128.175