## PPL
| PRIVILEGEPLUS Loyalty |  | 2019-12-30
2019-12-30
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 7 | 7
1 | Business analysis | 8 | 1 | Web Developer | 1 | 41.75 | 41.75 | 35.75 | 95.595 | 89.75
2 | Project Management | 46.76 | 5.845 | Android Developer | 1 | 30.75 | 30.75
3 | SRS, FS, User Manual | 40 | 5 | iOS Developer | 1 | 17.25 | 17.25
4 | Design and Prototype | 56 | 7 | PM | 1 | 5.845 | 5.845
| Development |  |  | BA | 1 | 1 | 1
5 | Application basic setup | 8 | 1 | Tech writer | 1 | 5 | 5
| Web App - System Admin |  |  | QA | 2 | 18.95 | 37.9
6 | Dashboard | 8 | 1 | Total | 9 | 127.545 | 146.495
7 | Membership Master (Add/edit/delete) | 8 | 1
8 | Merchant Master (Add/edit/delete) | 6 | 0.75 | Effort | 146.495 | + 1 Day (Deployment)
9 | Mall Master (Add/edit/delete) | 6 | 0.75 | Delivery Time | 127.545 | + 1 Day (Deployment)
10 | Tenant PRIVILEGEPLUS Device Master (Add/edit/delete) | 6 | 0.75
11 | Membership Type Master (Add/edit/delete) | 6 | 0.75
12 | Tenant Category Master (Add/edit/delete) | 6 | 0.75
13 | Loyalty Scheme Master (Add/edit/delete) | 6 | 0.75
14 | System Security- user management (Add/edit/delete) | 12 | 1.5
15 | Notifications and Automations | 24 | 3
16 | Flexibility of changing the conversion of Dhs to points in any day / week or month. | 8 | 1
Reports
17 | Reconciliation of each shop account and print a full data for that particular shop | 8 | 1
18 | Issued and redeemed Gift Card with the unique number of the customer | 8 | 1
19 | Issued and redeemed Gift Card with the unique number of the participating shop | 8 | 1
20 | Redeemed Gift Cards from the non-participating shops | 8 | 1
21 | Total sales of all the participating shops | 8 | 1
22 | Total gift cards redeemed (shop wise) | 8 | 1
23 | Daily, weekly, monthly or annual report | 8 | 1
Web API - Member
24 | Dashboard | 2 | 0.25
25 | Store Directory | 2 | 0.25
26 | Promotional offers | 2 | 0.25
27 | News | 2 | 0.25
28 | Services | 2 | 0.25
29 | Upcoming Events | 2 | 0.25
30 | Entertainment | 2 | 0.25
31 | Dining | 2 | 0.25
32 | About Us | 2 | 0.25
33 | Contact Us | 2 | 0.25
34 | Sign-up | 6 | 0.75
35 | Loyalty Profile | 4 | 0.5
36 | Membership Authentication | 6 | 0.75
37 | View Point balances | 2 | 0.25
38 | Feature all earned points and the conversion into Dhs | 6 | 0.75
39 | View transaction histories | 2 | 0.25
40 | Manage account profile | 4 | 0.5
41 | Push Notifications | 4 | 0.5
42 | Logout | 1 | 0.125
Web API - Tenant
43 | Dashboard | 2 | 0.25
44 | Login | 1 | 0.125
45 | Rewarding points | 2 | 0.25
46 | Checking Available points | 2 | 0.25
47 | Transaction History | 4 | 0.5
48 | Scan the purchase receipts (UI path) | 40 | 5
49 | Redemption of points against Gift Card | 4 | 0.5
50 | Void/Cancel/Return transactions | 12 | 1.5
51 | Classify transactions | 4 | 0.5
52 | General Sales transaction reports | 8 | 1
System Migration
53 | Migrate and retain existing customer and tenant data and all other required details | 40 | 5
Quality Assurance
54 | QA & Bug Fixing | 133.6 | 16.7
55 | UAT | 16 | 2
56 | Deployment per instance | 8 | 1
| Total Effort | 642.36 | 80.295
Assumptions
Only English language is considered
This estimation is purely based on assumptions. The effort may vary based on the actual functionalities.

## Android
| PRIVILEGEPLUS Loyalty |  | 2019-12-30
2019-12-30
| Module | Hours | Man Days
Development
1 | Application basic setup | 8 | 1
Mobile App - Member
2 | Dashboard | 8 | 1
3 | Store Directory | 12 | 1.5
4 | Promotional offers | 6 | 0.75
5 | News | 6 | 0.75
6 | Services | 4 | 0.5
7 | Upcoming Events | 6 | 0.75
8 | Entertainment | 6 | 0.75
9 | Dining | 4 | 0.5
10 | About Us | 4 | 0.5
11 | Contact Us | 4 | 0.5
12 | Sign-up | 8 | 1
13 | Loyalty Profile | 8 | 1
14 | Membership Authentication | 8 | 1
15 | View Point balances | 4 | 0.5
16 | Feature all earned points and the conversion into Dhs | 8 | 1
17 | View transaction histories | 4 | 0.5
18 | Manage account profile | 4 | 0.5
19 | Push Notifications | 24 | 3
20 | Logout | 2 | 0.25
Tablet App - Tenant
21 | Dashboard | 8 | 1
22 | Login | 8 | 1
23 | Rewarding points | 4 | 0.5
24 | Checking Available points | 4 | 0.5
25 | Transaction History | 4 | 0.5
26 | Scan the purchase receipts (UI path) | 24 | 3
27 | Redemption of points against Gift Card | 8 | 1
28 | Void/Cancel/Return transactions | 24 | 3
29 | Classify transactions | 8 | 1
30 | General Sales transaction reports | 16 | 2
Quality Assurance
31 | QA & Bug Fixing | 98.4 | 12.3
| Total Effort | 344.4 | 43.05
Assumptions
Only English language is considered
1. This estimation is purely based on assumptions, since mobile app screens are not provided. The effort may vary based on the actual functionalities. 2. The estimation is done for iOS and Android Portrait mode. 3. Mobile App testing can be done only with the available devices.

## iOS
| PRIVILEGEPLUS Loyalty |  | 2019-12-30
2019-12-30
| Module | Hours | Man Days
Development
1 | Application basic setup | 8 | 1
Mobile App - Member
2 | Dashboard | 8 | 1
3 | Store Directory | 12 | 1.5
4 | Promotional offers | 6 | 0.75
5 | News | 6 | 0.75
6 | Services | 4 | 0.5
7 | Upcoming Events | 6 | 0.75
8 | Entertainment | 6 | 0.75
9 | Dining | 4 | 0.5
10 | About Us | 4 | 0.5
11 | Contact Us | 4 | 0.5
12 | Sign-up | 8 | 1
13 | Loyalty Profile | 8 | 1
14 | Membership Authentication | 8 | 1
15 | View Point balances | 4 | 0.5
16 | Feature all earned points and the conversion into Dhs | 8 | 1
17 | View transaction histories | 4 | 0.5
18 | Manage account profile | 4 | 0.5
19 | Push Notifications | 24 | 3
20 | Logout | 2 | 0.25
Quality Assurance
22 | QA & Bug Fixing | 55.2 | 6.9
| Total Effort | 193.2 | 24.15
Assumptions
Only English language is considered
1. This estimation is purely based on assumptions, since mobile app screens are not provided. The effort may vary based on the actual functionalities. 2. The estimation is done for iOS and Android Portrait mode. 3. Mobile App testing can be done only with the available devices.