## Data Migration
Activity description | Hours | Days
Initiation |  |  | 7.5
Preprwork, R&D and discussions | 12 | 1.5
Documentation | 8 | 1
Database Design | 16 | 2
Project management | 6.975 | 0.87187
Development
Query design Item file | 4 | 0.5
Query design Order file | 8 | 1
Query design Replacement file | 2 | 0.25
Query design stock file | 2 | 0.25
Query design Tdsample | 8 | 1
Stored Procedure (2 hrs x 5) | 10 | 1.25
Job Creation & scheduling (1 hr x 5) | 5 | 0.625
Export daily and weekly (1.5 hr x 5) | 7.5 | 0.9375
Testing & debugging | 24.3162 | 3.0395
Total effort | 113.7912 | 14.2239