## Web
VEZEETA 24 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 35.2 | 4.4 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 4.4 | 4.4
Design and Prototype (mobile & Web) | 64 | 8 | Jr Developer | 1 | 25 | 25 | 49 | 48.5
Development |  |  | Sr Developer | 1 | 24 | 24
Application Basic setup | 8 | 1 | Mobile API | 1 | 22.05 | 22.05
Admin |  |  | QA | 2 | 11.4875 | 22.975
Manage countries | 6 | 0.75 | Total |  |  | 115.425
Manage states | 6 | 0.75
Manage cities | 6 | 0.75 |  | Days | Months
Manage areas | 6 | 0.75 | Total Effort | 115.425 | 5.7713
Manage speciality | 6 | 0.75 | Delivery Timeline | 49.4875 | 2.4744
Manage super specialities | 6 | 0.75
Manage categories | 6 | 0.75
Manage doctor profiles | 16 | 2
Manage schedules | 12 | 1.5
Manage doctor offices | 12 | 1.5
Manage promocodes | 12 | 1.5
Dashboard (doctors / patients / collections ) | 24 | 3
Manage comments (approve / Reject) | 8 | 1
Manage reviews | 8 | 1
Manage offers | 16 | 2
Pharamcy orders (orders, payments, deliveries) | 24 | 3
API
Search by speciality, location, schedule, fess etc | 12 | 1.5
Doctor | 12 | 1.5
Patient | 12 | 1.5
Doctor login | 12 | 1.5
patient login | 12 | 1.5 | Using Twillio. Must pay for subscription depending on usage (simple chat features)
Schedules | 16 | 2
Bookings | 16 | 2
Payments | 16 | 2
Offers | 16 | 2
Sorting | 12 | 1.5
filtering | 12 | 1.5
categories | 6 | 0.75
maps | 16 | 2
Integrations |  | 0
Maps | 12 | 1.5
Payment G/W | 12 | 1.5
Social login | 12 | 1.5
SQA
QA & Bug fixing | 135.8 | 16.975
UAT | 40 | 5
Deployment | 8 | 1
Total | 743 | 92.875
vvvcnmnmvbn

## Mobile
VEZEETA 24 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1 | 33 | 33
Patient |  |  |  |  | iOS Developer | 1 | 33 | 33
Splash screen |  |  |  |  | QA | 1 | 0 | 0
Login |  |  |  |  | Total |  |  | 66
forgot passowrd
remember password
Home screen
register patient
Book a doctor appointment
Search by speciality, area, location
Search by doctor name
list doctors (AREA, FEES, WAITING TIME, NAME, SPECIALITY, RATINGS, # of visitors)
book doctor (namme, description, ratings fees, waiting time, schedules, clinic locations, reviews)
sort by most reccomended, price-hogh to low, price-low to high, waiting time)
filter by (Hostital-clinic, examination fees, payment method, availability, gender, title)
map view (Search by area)
Book Telehealth call
Search by medical area
sort by most reccomended, price-hogh to low, price-low to high)
filter by (appointment type-[phone,video], entity -[hospital,clinic], examination fees-range, payment method, availability, gender, title)
list doctors (AREA, FEES, WAITING TIME, NAME, SPECIALITY, RATINGS, # of visitors)
book doctor (namme, description, ratings fees, waiting time, schedules, clinic locations, reviews)
register or sign in (if not signed in)
Make payment
Offers
List categories
Promotions ( sliding window)
Scrolling offers
Trending
Most requested
search
selected Offer page (images, # of views, # of bookings, name location, price,discount, slect schedule, reviews, description, provider, map)
Book offer
register or sign in (if not signed in)
Pharmacy
Order with prescription (take picture)
Take product picture
place order (without payment) |  |  |  |  | Actual purchase is offline
Appointments
register or sign in (if not signed in)
View appointments
appointment details
More
Settings (change country & language)
Contact US
About us
Favourites
Sign in
Doctors
Sign in
Register
Add / manage offices
Add / manage Services
Manage schedules
View / manage appointments
View reviews
View comments
Respond to comments
View payment history
Add offers
SQA
QA & Bug fixing | 0 | 0 | 0 | 0
UAT |  | 0 |  | 0
Deployment |  | 0 |  | 0
| 0 | 0 | 369.6 | 0
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.