## Web
VEZEETA 24 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 35.2 | 4.4 | Tech Writer | 1 | 4 | 4
SRS,FS,User Manual | 32 | 4 | PM | 1 | 4.4 | 4.4
Design and Prototype (mobile & Web) | 64 | 8 | Jr Developer | 1 | 25 | 25 | 49 | 48.5
Development |  |  | Sr Developer | 1 | 24 | 24
Application Basic setup | 8 | 1 | Mobile API | 1 | 22.05 | 22.05
Admin |  |  | QA | 2 | 11.4875 | 22.975
Manage countries | 6 | 0.75 | Total |  |  | 115.425
Manage states | 6 | 0.75
Manage cities | 6 | 0.75 |  | Days | Months
Manage areas | 6 | 0.75 | Total Effort | 115.425 | 5.7713
Manage speciality | 6 | 0.75 | Delivery Timeline | 49.4875 | 2.4744
Manage super specialities | 6 | 0.75
Manage categories | 6 | 0.75
Manage doctor profiles | 16 | 2
Manage schedules | 12 | 1.5
Manage doctor offices | 12 | 1.5
Manage promocodes | 12 | 1.5
Dashboard (doctors / patients / collections ) | 24 | 3
Manage comments (approve / Reject) | 8 | 1
Manage reviews | 8 | 1
Manage offers | 16 | 2
Pharamcy orders (orders, payments, deliveries) | 24 | 3
API
Search by speciality, location, schedule, fess etc | 12 | 1.5
Doctor | 12 | 1.5
Patient | 12 | 1.5
Doctor login | 12 | 1.5
patient login | 12 | 1.5 | Using Twillio. Must pay for subscription depending on usage (simple chat features)
Schedules | 16 | 2
Bookings | 16 | 2
Payments | 16 | 2
Offers | 16 | 2
Sorting | 12 | 1.5
filtering | 12 | 1.5
categories | 6 | 0.75
maps | 16 | 2
Integrations |  | 0
Maps | 12 | 1.5
Payment G/W | 12 | 1.5
Social login | 12 | 1.5
SQA
QA & Bug fixing | 135.8 | 16.975
UAT | 40 | 5
Deployment | 8 | 1
Total | 743 | 92.875
vvvcnmnmvbn

## Mobile
VEZEETA 24 September 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
| Android |  | IOS |  | AndroidDeveloper | 1.5 | 31.3333 | 47
Patient |  |  |  |  | QA | 1.5 | 14.9667 | 22.45
Splash screen | 8 | 1 | 8 | 1 | Total |  | 46.3 | 69.45
Login | 6 | 0.75 | 6 | 0.75
forgot passowrd | 6 | 0.75 | 6 | 0.75 | Delivery | 46.3 | Per track
remember password | 6 | 0.75 | 6 | 0.75 | Estimated effort | 69.45
Home screen | 10 | 1.25 | 10 | 1.25
register patient | 8 | 1 | 8 | 1
Book a doctor appointment | 8 | 1 | 8 | 1
Search by speciality, area, location | 8 | 1 | 8 | 1
Search by doctor name | 8 | 1 | 8 | 1
list doctors (AREA, FEES, WAITING TIME, NAME, SPECIALITY, RATINGS, # of visitors) | 8 | 1 | 8 | 1
book doctor (namme, description, ratings fees, waiting time, schedules, clinic locations, reviews) | 8 | 1 | 8 | 1
sort by most reccomended, price-hogh to low, price-low to high, waiting time) | 8 | 1 | 8 | 1
filter by (Hostital-clinic, examination fees, payment method, availability, gender, title) | 8 | 1 | 8 | 1
map view (Search by area) | 8 | 1 | 8 | 1
Book Telehealth call
Search by medical area | 8 | 1 | 8 | 1
sort by most reccomended, price-hogh to low, price-low to high) | 6 | 0.75 | 6 | 0.75
filter by (appointment type-[phone,video], entity -[hospital,clinic], examination fees-range, payment method, availability, gender, title) | 8 | 1 | 8 | 1
list doctors (AREA, FEES, WAITING TIME, NAME, SPECIALITY, RATINGS, # of visitors) | 6 | 0.75 | 6 | 0.75
book doctor (namme, description, ratings fees, waiting time, schedules, clinic locations, reviews) | 8 | 1 | 8 | 1
register or sign in (if not signed in) | 6 | 0.75 | 6 | 0.75
Make payment | 24 | 3 | 24 | 3
Offers
List categories | 8 | 1 | 8 | 1
Promotions ( sliding window) | 8 | 1 | 8 | 1
Scrolling offers | 6 | 0.75 | 6 | 0.75
Trending | 6 | 0.75 | 6 | 0.75
Most requested | 6 | 0.75 | 6 | 0.75
search | 8 | 1 | 8 | 1
selected Offer page (images, # of views, # of bookings, name location, price,discount, slect schedule, reviews, description, provider, map) | 8 | 1 | 8 | 1
Book offer | 8 | 1 | 8 | 1
register or sign in (if not signed in) | 8 | 1 | 8 | 1
Pharmacy
Order with prescription (take picture) | 10 | 1.25 | 10 | 1.25
Take product picture | 6 | 0.75 | 6 | 0.75 | Actual purchase is offline
place order (without payment) | 6 | 0.75 | 6 | 0.75
Appointments
register or sign in (if not signed in) | 8 | 1 | 8 | 1
View appointments | 6 | 0.75 | 6 | 0.75
appointment details | 6 | 0.75 | 6 | 0.75
More
Settings (change country & language) | 8 | 1 | 8 | 1
Contact US | 4 | 0.5 | 4 | 0.5
About us | 4 | 0.5 | 4 | 0.5
Favourites | 4 | 0.5 | 4 | 0.5
Sign in | 6 | 0.75 | 6 | 0.75
Doctors
Sign in | 6 | 0.75 | 6 | 0.75
Register | 6 | 0.75 | 6 | 0.75
Add / manage offices | 8 | 1 | 8 | 1
Add / manage Services | 8 | 1 | 8 | 1
Manage schedules | 8 | 1 | 8 | 1
View / manage appointments | 8 | 1 | 8 | 1
View reviews | 6 | 0.75 | 6 | 0.75
View comments | 6 | 0.75 | 6 | 0.75
Respond to comments | 6 | 0.75 | 6 | 0.75
View payment history | 6 | 0.75 | 6 | 0.75
Add offers |  | 0 |  | 0
|  | 0 |  | 0
SQA
QA & Bug fixing | 131.6 | 16.45 | 131.6 | 16.45
UAT | 40 | 5 | 40 | 0
Deployment | 8 | 1 | 8 | 0
| 555.6 | 69.45 | 555.6 | 63.45
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.