## Sheet1
Project Initiation | Hours | Days
Project management | 25.8 | 3.225
Business Analysis / Documentation | 24 | 3
Design (UI / UX) | 24 | 3 | Activity | Resources | Delivery Days | Total effort
Development |  | 0 | PM | 1 | 3.225 | 3.225
Environment Prep | 6 | 0.75 | BA | 1 | 3 | 3
User Registration ( Forgot pw, remember pw, validate email, Assign role, assign project) | 12 | 1.5 | Design | 1 | 3 | 3
Login (retrieve role, profile data, projects assigned) | 6 | 0.75 | Development | 1.5 | 21.5 | 32.25
Check for material availability Screen + Lookup logic in SAP | 4 | 0.5 | QA | 1.5 | 8.1917 | 12.2875
Sort , filter material availability results | 6 | 0.75 |  | Sum | 38.9167 | 53.7625
Create material (code description, SKU etc) | 4 | 0.5
Select material, quantity + add to cart | 6 | 0.75
raise PO | 6 | 0.75 |  | Delivery Days | 35.6917
Create PO | 6 | 0.75 |  | Total Effort | 53.7625
Create Goods Receipts | 6 | 0.75
Create QR Code | 6 | 0.75
Print QR Code | 6 | 0.75
Assign goods to project | 6 | 0.75
Approval cycle (workflow for PO, GR, Project Assignment) | 24 | 3
Issue material | 6 | 0.75
update stock | 6 | 0.75
Simple Stock & inventory management (manage mterials) | 32 | 4
goods return process | 6 | 0.75
Transfer stock between projects | 12 | 1.5
reporting (min 4 reports, 6 hrs for each additional report) | 24 | 3
Admin functionality | 32 | 4
Logging / auditing / authentication / Authorization | 12 | 1.5
Web service integrations | 24 | 3
QA
QA + UAT | 90.3 | 11.2875
Deployment | 8 | 1
Sum | 430.1 | 53.7625
Assumptions
Payment processing not considered
Multi tenancy not considered
Integration wit AD not considered
Simple web integrations no more than 6-10 service end points
Technology
ASP.net / PHP + Mssql / Mysql + Apache / IIS + HTML5, CSS, Jquery