## mobile
WaterWa |  |  |  | 2020-04-26
Sunday
Android
Module | Android |  | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 |  | 0
Development |  |  |  |  | Sr Developer | 1 | 11.5 | 11.5 | 21.625 | 25.5 | 25.375 | 25.5
[5 empty] | Jr Developer | 1 | 14 | 14
Design Rendering | 16 | 2 | 16 | 2 | QA | 1.5 | 9.6792 | 14.5188
Application basic setup | 8 | 1 | 6 | 0.75 | Total | 3 | 25.5 | 40.0187
Splash Screen | 2 | 0.25 | 2 | 0.25
Select City Page
Select Country | 3 | 0.375 | 3 | 0.375
Select City | 2 | 0.25 | 2 | 0.25 | Effort | 40.0187 | + 1 Day (Deployment)
Register Page |  |  |  |  | Delivery Time | 23.6792 | + 1 Day (Deployment)
Name and Email | 2 | 0.25 | 2 | 0.25
Select Area | 3 | 0.375 | 3 | 0.375
Add Address | 3 | 0.375 | 3 | 0.375
Home Page |  |  |  |  | IOS
Filter Option | 16 | 2 | 16 | 2 |  | No | Man Days | Total Effort
Two Category (Two tabs) | 10 | 1.25 | 12 | 1.5 | Designer | 1 |  | 0
Show Cart | 12 | 1.5 | 12 | 1.5 | Sr Developer | 1 | 12.5 | 12.5 | 71.0625 | 26.5 | 26.375 | 26.5
Listing Shops for each category | 8 | 1 | 6 | 0.75 | Jr Developer | 1 | 14 | 14
Shop Page | 10 | 1.25 | 10 | 1.25 | QA | 1.5 | 9.9792 | 14.9688
Home Silder Page |  |  |  |  | Total | 3 | 26.5 | 41.4688
My Account | 2 | 0.25 | 2 | 0.25
My Orders(view orders) | 8 | 1 | 7 | 0.875
WhatsApp integration | 8 | 1 | 8 | 1
Help Centre(customer care email and business inquiries) | 8 | 1 | 7 | 0.875 | Effort | 41.4688 | + 1 Day (Deployment)
Bilingual(english& arabic) | 16 | 2 | 24 | 3 | Delivery Time | 23.9792
My coupons | 8 | 1 | 8 | 1
My Address Book(add one or more address or delete address) | 8 | 1 | 8 | 1
Checkout Page |  |  |  |  | Activity | Hrs | Days
Order Summary | 10 | 1.25 | 8 | 1 | UI / UX Design (Android + IOS) | 40 | 5
Thank You page(also cancel order) | 8 | 1 | 8 | 1
Apply coupon | 8 | 1 | 8 | 1 | Approx Delivery Time (IOS + Android) | 5 + 24 + 1
Payment gateway | 24 | 3 | 8 | 1 | Design + Dvelopment & QA + Deployment
Admin Panel(only iOS)
Listing the orders | 0 | 0 | 8 | 1
Listing Completed Orders | 0 | 0 | 6 | 0.75
Call Customer | 0 | 0 | 8 | 1 |  | 70.4
Quality Assurance
QA & Bug Fixing | 84.15 | 10.5188 | 87.75 | 10.9688
UAT | 32 | 4 | 32 | 4
Deployment per instance | 8 | 1 | 8 | 1
Total Effort | 311.15 | 38.8937 | 322.75 | 40.3438
Assumptions 1.This estimation is done only for portarit mode of the applictaion. 2.The estimation may vary with changes or addition of new features.
Assumptions 1.This estimation is done only for portarit mode of the applictaion. 2.The estimation may vary with changes or addition of new features.