## mobile
WaterWa |  |  |  | 28/04/2020
Tuesday
Android
Module | Android |  | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 |  | 0
Development |  |  |  |  | Sr Developer | 1 | 10 | 10 | 21.375 | 24 | 25.125 | 24
[5 empty] | Jr Developer | 1 | 14 | 14
Design Rendering | 16 | 2 | 16 | 2 | QA | 1.5 | 9.6042 | 14.4062
Application basic setup | 8 | 1 | 6 | 0.75 | Total | 3 | 24 | 38.4062
Splash Screen | 2 | 0.25 | 2 | 0.25
Select City Page
Select Country | 3 | 0.375 | 3 | 0.375
Select City | 2 | 0.25 | 2 | 0.25 | Effort | 38.4062 | + 1 Day (Deployment)
Register Page |  |  |  |  | Delivery Time | 23.6042 | + 1 Day (Deployment)
Name and Email | 2 | 0.25 | 2 | 0.25
Select Area | 3 | 0.375 | 3 | 0.375
Add Address | 3 | 0.375 | 3 | 0.375
Home Page |  |  |  |  | IOS
Filter Option | 16 | 2 | 16 | 2 |  | No | Man Days | Total Effort
Two Category (Two tabs) | 10 | 1.25 | 12 | 1.5 | Designer | 1 |  | 0
Show Cart | 12 | 1.5 | 12 | 1.5 | Sr Developer | 1 | 11 | 11 | 70.3375 | 25 | 26.125 | 25
Listing Shops for each category | 8 | 1 | 6 | 0.75 | Jr Developer | 1 | 14 | 14
Payment page | 10 | 1.25 | 10 | 1.25 | QA | 1.5 | 9.9042 | 14.8562
Home Silder Page |  |  |  |  | Total | 3 | 25 | 39.8563
My Account | 2 | 0.25 | 2 | 0.25
My Orders(view orders) | 8 | 1 | 7 | 0.875
Whatsup integration | 8 | 1 | 8 | 1
Help Centre(customer care email and business inquiries) | 8 | 1 | 7 | 0.875 | Effort | 39.8563 | + 1 Day (Deployment)
Bilingual(english& arabic) | 16 | 2 | 24 | 3 | Delivery Time | 23.9042
My Address Book(add one or more address or delete address) | 8 | 1 | 8 | 1
View Coupons | 8 | 1 | 8 | 1
Checkout Page |  |  |  |  | Activity | Hrs | Days
Order Summary | 10 | 1.25 | 8 | 1 | UI / UX Design (Android + IOS + Web) | 40 | 5
Thank You page(also cancel order) | 8 | 1 | 8 | 1
Appl Coupons | 6 | 0.75 | 6 | 0.75 | Approx Delivery Time (IOS + Android) | 5 + 24 + 1
Payment gateway | 24 | 3 | 8 | 1 | Design + Dvelopment & QA + Deployment
Admin Panel(only iOS)
Listing the orders | 0 | 0 | 8 | 1
Listing Completed Orders | 0 | 0 | 6 | 0.75
Call Customer | 0 | 0 | 8 | 1 |  | 70.4
Quality Assurance
QA & Bug Fixing | 83.25 | 10.4062 | 86.85 | 10.8562
UAT | 32 | 4 | 32 | 4
Deployment per instance | 8 | 1 | 8 | 1
Total Effort | 308.25 | 38.5312 | 319.85 | 39.9813
Assumptions 1.This estimation is done only for portarit mode of the applictaion. 2.The estimation may vary with changes or addition of new features.
Assumptions 1.This estimation is done only for portarit mode of the applictaion. 2.The estimation may vary with changes or addition of new features.

## Admin
| WaterWa |  | 28/4/2020
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 0 | 0
1 | Business analysis | 18 | 2.25 | Sr Developer | 1 | 7 | 7 | 15.25 | 15.5
2 | Project Management | 12.2 | 1.525 | Jr Developer | 1 | 8.5 | 8.5
3 | SRS,FS,User Manual | 8 | 1 | PM | 1 | 1.525 | 1.525
4 | Design and Prototype | 0 | 0 | BA | 1 | 2.25 | 2.25
| Development |  |  | Tech writer | 1 | 1 | 1
5 | Application basic setup | 8 | 1 | QA | 1 | 10.4125 | 10.4125
| Admin Panel |  |  | Sum |  | 30.6875 | 30.6875
| Login/logout (2 admin users and 2 roles) | 6 | 0.75
| Dashboard | 8 | 1 | Effort | 30.6875 | + 1 Day (Deployment)
| Manage Categories (add/edit/delete) ex.water/Beverages | 8 | 1 | Delivery Time | 21.1625 | + 1 Day (Deployment)
| Manage Brands (add/edit/delete) | 8 | 1
| Brand Email,Brand Logo,Brand Banner,Minimum Order,No of days of delivery, cities to deliver |  | 0
| Payment type (COD or Credit Card or Both) | 6 | 0.75 | API Development | 6.4125
| Prioritize/Rank brands | 6 | 0.75
| Filter tab (add/edit/delete) sub categories of brands | 8 | 1
| Manage Products (add/edit/delete) | 6 | 0.75
| product name attach to brand & brand filter | 6 | 0.75
| Product price,discount,description | 6 | 0.75
| Add Banners to home page & attach it to shop | 6 | 0.75
| Notification: text notification | 6 | 0.75
| Manage coupons with expriy date and amount of discount; Distribute coupons to individualls or groups) | 16 | 2
| View Status of the orders(pending, completed) | 6 | 0.75
| Export reports | 6 | 0.75
| Download as PDF, excel files | 6 | 0.75
0
Quality Assurance
| QA & Bug Fixing | 51.3 | 6.4125
| UAT | 32 | 4
| Deployment per instance | 8 | 1
| Total Effort |  | 31.4375
Assumptions
The effort may change after a detailed system study