## Mobile
Aldar Retail 06 October 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
Project Initiation |  |  |  |  | AndroidDeveloper | 1 |  | 0
Business analysis |  |  |  |  | iOS Developer | 1 |  | 0
Project Management |  |  |  |  | QA | 1 | 37.625 | 37.625
SRS,FS,User Manual |  |  |  |  | Mobile API
Design and Prototype (mobile
| Android |  | IOS
Online Booking/Plan your day
Register,Login | 8 | 1 | 8 | 1
Book Now |  | 0 |  | 0
Restaurants, Cinema, Kidzania,Ferrai World,etc | 10 | 1.25 | 10 | 1.25
Pay (Payment Integration) | 20 | 2.5 | 20 | 2.5
Cerdit cards, debit cards, internet banking | 8 | 1 | 8 | 1
Search Categories & Store Listing
Store & Service Directory/locator(Not a simple list) | 10 | 1.25 | 10 | 1.25
Product recommendations & filter search mapping | 10 | 1.25 | 10 | 1.25
Upload pictures and search for similar products recommend form existing mall retailer’s website/online offering | 16 | 2 | 16 | 2
Way Finding
Dynamic & interactive 3D way mapping | 20 | 2.5 | 20 | 2.5
Interactive AR map with easy navigation between stores/floors | 20 | 2.5 | 20 | 2.5
Events & Promotion
Events – update customers on ongoing events & promotion with real time information | 10 | 1.25 | 10 | 1.25
Promotion – Option to digitalize mall promotions – e-coupons etc | 10 | 1.25 | 10 | 1.25
Customer Service
Customer Service & Support-What’s app number, Video Call, Helpdesk number, Lost & Found integration | 16 | 2 | 16 | 2
Route Customer Service | 8 | 1 | 8 | 1
Help Tourists/Customers |  | 0 |  | 0
hotels around, taxi booking, Bus services to the hotels etc | 10 | 1.25 | 10 | 1.25
Social Blog
Post Video Content | 10 | 1.25 | 10 | 1.25
Curate & post new collection video catalogue, new offer, new promotion video | 10 | 1.25 | 10 | 1.25
Category Listing with example | 8 | 1 | 8 | 1
Other Features
Push notifications | 12 | 1.5 | 12 | 1.5
Data Collection(customers downloading the app, buying behavior, search, navigation) | 10 | 1.25 | 10 | 1.25
Add on's(new apps,vendors) | 8 | 1 | 8 | 1
Content Management Support(3months) | 10 | 1.25 | 10 | 1.25
Geo-targeting selection | 10 | 1.25 | 10 | 1.25
Bilingual(Arabic& English) | 10 | 1.25 | 10 | 1.25
Integration
Aldar retail assets Integration |  | 0 |  | 0
Yas Mall, | 10 | 1.25 | 10 | 1.25
WTC | 8 | 1 | 8 | 1
Al Jimi Mall | 10 | 1.25 | 10 | 1.25
Service Integration(Api Integration) |  | 0 |  | 0
Yas Mall Akyasi -delivery service app, | 10 | 1.25 | 10 | 1.25
We shop for you – personal shopping & delivery service (park of Akyasi App) | 8 | 1 | 8 | 1
My Park – parking reservation app, | 8 | 1 | 8 | 1
Aldar Darna mall loyalty program, | 8 | 1 | 8 | 1
Etihad loyalty program | 8 | 1 | 8 | 1
Mall gift Card | 6 | 0.75 | 6 | 0.75
Careem | 8 | 1 | 8 | 1
E-commerce (Later stage) | 8 | 1 | 8 | 1
Ticket Booking(Api Integration or redirected to web page) |  | 0 |  | 0
Cinema | 8 | 1 | 8 | 1
Kidzania | 8 | 1 | 8 | 1
Ferrari world | 8 | 1 | 8 | 1
Yas Water World | 8 | 1 | 8 | 1
Warner Bros | 8 | 1 | 8 | 1
CLYM | 6 | 0.75 | 6 | 0.75
Magic Planet | 6 | 0.75 | 6 | 0.75
Digital E-coupon(Api Integration) | 10 | 1.25 | 10 | 1.25
Table Reservation | 12 | 1.5 | 12 | 1.5
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
SQA
QA & Bug fixing | 150.5 | 18.8125 | 150.5 | 18.8125
UAT |  | 0 |  | 0
Deployment |  | 0 |  | 0
| 580.5 | 72.5625 | 580.5 | 72.5625
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.