## Mobile
Aldar Retail 06 October 2020
| Hrs | Days | Hrs | Days | Resources | # | Days | Total
Project Initiation |  |  |  |  | Business analysis | 1 | 5 | 5
Business analysis |  |  |  |  | Project Management | 1 | 4.75 | 4.75
Project Management |  | 0 |  |  | SRS,FS,User Manual | 1 | 4 | 4
SRS,FS,User Manual |  |  |  |  | Design and Prototype (mobile ) | 1 | 12 | 12
Design and Prototype (mobile ) |  |  |  |  | AndroidDeveloper | 1.5 | 31.6667 | 47.5 | 47.5
| Android |  | IOS |  | QA | 1.5 | 16.5417 | 24.8125
Online Booking/Plan your day |  |  |  |  | Mobile API
Register,Login | 8 | 1 | 8 | 1
Book Now |  | 0 |  | 0 |  | Days | Months
Restaurants, Cinema, Kidzania,Ferrai World,etc | 10 | 1.25 | 10 | 1.25 | Total effort (Android+IOS+API) | 194.125 | 9.7063
Pay (Payment Integration) | 20 | 2.5 | 20 | 2.5 | Development Timeline | 65.2083 | 3.2604
Cerdit cards, debit cards, internet banking | 8 | 1 | 8 | 1 | API Effort | 19
Search Categories & Store Listing
Store & Service Directory/locator(Not a simple list) | 10 | 1.25 | 10 | 1.25
Product recommendations & filter search mapping | 10 | 1.25 | 10 | 1.25
Upload pictures and search for similar products recommend form existing mall retailer’s website/online offering | 16 | 2 | 16 | 2
Way Finding
Dynamic & interactive 3D way mapping | 0 | 0 | 0 | 0
Interactive AR map with easy navigation between stores/floors | 0 | 0 | 0 | 0
Events & Promotion
Events – update customers on ongoing events & promotion with real time information | 10 | 1.25 | 10 | 1.25
Promotion – Option to digitalize mall promotions – e-coupons etc | 10 | 1.25 | 10 | 1.25
Customer Service
Customer Service & Support-What’s app number, Helpdesk number, Lost & Found integration | 16 | 2 | 16 | 2
Route Customer Service | 8 | 1 | 8 | 1
Help Tourists/Customers |  | 0 |  | 0
hotels around, taxi booking, Bus services to the hotels etc | 10 | 1.25 | 10 | 1.25
Social Blog
Post Video Content | 10 | 1.25 | 10 | 1.25
Curate & post new collection video catalogue, new offer, new promotion video | 10 | 1.25 | 10 | 1.25
Category Listing with example | 8 | 1 | 8 | 1
Other Features
Push notifications | 12 | 1.5 | 12 | 1.5
Data Collection(customers downloading the app, buying behavior, search, navigation) | 10 | 1.25 | 10 | 1.25
Add on's(new apps,vendors) | 8 | 1 | 8 | 1
Content Management Support(3months) | 10 | 1.25 | 10 | 1.25
Geo-targeting selection | 0 | 0 | 0 | 0
Bilingual(Arabic& English) | 10 | 1.25 | 10 | 1.25
Integration
Aldar retail assets Integration |  | 0 |  | 0
Yas Mall, | 10 | 1.25 | 10 | 1.25
WTC | 8 | 1 | 8 | 1
Al Jimi Mall | 10 | 1.25 | 10 | 1.25
Service Integration(Api Integration) |  | 0 |  | 0
Yas Mall Akyasi -delivery service app, | 10 | 1.25 | 10 | 1.25
We shop for you – personal shopping & delivery service (park of Akyasi App) | 8 | 1 | 8 | 1
My Park – parking reservation app, | 8 | 1 | 8 | 1
Aldar Darna mall loyalty program, | 8 | 1 | 8 | 1
Etihad loyalty program | 8 | 1 | 8 | 1
Mall gift Card | 6 | 0.75 | 6 | 0.75
Careem | 8 | 1 | 8 | 1
E-commerce (Later stage) | 8 | 1 | 8 | 1
Ticket Booking(Api Integration or redirected to web page) |  | 0 |  | 0
Cinema | 8 | 1 | 8 | 1
Kidzania | 8 | 1 | 8 | 1
Ferrari world | 8 | 1 | 8 | 1
Yas Water World | 8 | 1 | 8 | 1
Warner Bros | 8 | 1 | 8 | 1
CLYM | 6 | 0.75 | 6 | 0.75
Magic Planet | 6 | 0.75 | 6 | 0.75
Digital E-coupon(Api Integration) | 10 | 1.25 | 10 | 1.25
Table Reservation | 12 | 1.5 | 12 | 1.5
API |  | 0 |  | 0 | Hours | Days
API Development (payments, Credit cards service directory, search, product reccomendations, upload pictures, events, promotions, hotel listing, taxi services, bus services, Blog, third party API) | 0 | 0 |  | 0 | 152 | 19
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
|  | 0 |  | 0
SQA
QA & Bug fixing | 150.5 | 18.8125 | 150.5 | 18.8125
UAT | 40 | 5 | 40 | 5
Deployment | 8 | 1 | 8 | 1
| 578.5 | 72.3125 | 578.5 | 72.3125
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app. 4. Does not include GEO Targeting